Evaluation

of the

Improved Climate Change Scenarios Program

Final Report

November 2010

Report Clearance Steps

| Planning phase completed | July 2009 |
| --- | --- |
| Report sent for management response | May 2010 |
| Management response received | October 2010 |
| Report completed | October 2010 |
| Report approved by Departmental Evaluation Committee (DEC) | November 2010 |

Abbreviations used in the report

| ADM | Assistant Deputy Minister |
| --- | --- |
| AEB | Audit and Evaluation Branch |
| AIRD | Adaptation and Impacts Research Division |
| AIRG | Adaptation and Impacts Research Group |
| AIRS | Adaptation and Impacts Research Section |
| ASTD | Atmospheric Science and Technology Directorate |
| CA | Conservation Authorities |
| CAA | Clean Air Agenda |
| CanESM1 | Canadian Earth System Model |
| CanESM2 | Canada’s new Earth System Model |
| CCBFC | Canadian Commission on Building and Fire Codes |
| CCC | Canadian Climate Centre |
| CCCma | Canadian Centre for Climate Modelling and Analysis |
| CCCSN | Canadian Climate Change Scenarios Network |
| CCIS | Climate Change Interim Strategy |
| CESD | Commissioner of the Environment and Sustainable Development |
| CFCAS | Canadian Foundation for Climate and Atmospheric Sciences |
| CMOC | Canadian Model of Ocean Carbon |
| CRCMD | Canadian Network for Regional Climate Modelling and Diagnostics |
| CRD | Climate Research Division |
| C-SPARC | Canadian Stratospheric Processes and their Role in Climate |
| CSA | Canadian Standards Association |
| CSRIs | Codes, Standards and Risk Instruments |
| CTEM | Canadian Terrestrial Ecosystem Model |
| CWA | Canadian Wildlife Association |
| DEC | Departmental Evaluation Committee |
| DFAIT | Department of Foreign Affairs and International Trade |
| DFO | Department of Fisheries and Oceans |
| DG | Director General |
| DGMC | Director General Management Committee |
| DGTLCC | Director General Theme Leads Coordinating Committee |
| DPR | Departmental Performance Report |
| EC | Environment Canada |
| FTE | Full Time Equivalent |
| GCM | global climate model |
| GHG | greenhouse gas |
| GOAPP | Global Ocean- Atmosphere Prediction and Predictability |
| HC | Health Canada |
| HMARF | Horizontal Management Accountability and Reporting Framework |
| INAC | Indian and Northern Affairs Canada |
| IPCC | Intergovernmental Panel on Climate Change |
| MOU | Memorandum of Understanding |
| MSC | Meteorological Service of Canada |
| NAQHI | National Air Quality and Health Index |
| NARCCAP | North American Regional Climate Change Assessment Program |
| NBCC | National Building Code of Canada |
| NCR | National Capital Region |
| NRC | National Research Council |
| NRCan | Natural Resources Canada |
| NRTEE | National Roundtable on the Environment and the Economy |
| NSERC | National Sciences and Engineering Research Council |
| OCCIAR | Ontario Centre for Climate Impacts and Adaptation Resources |
| OPG | Outcome Project Group |
| OPP | Outcome Project Plan |
| PAA | Program Activity Architecture |
| PC | Parks Canada |
| PCIC | Pacific Climate Impacts Consortium |
| PHAC | Public Health Agency of Canada |
| PiP | Projections in Practice Program |
| RCMs | regional climate models |
| RPPs | Reports on Plans and Priorities |
| TAC | Transportation Association of Canada |
| TC | Transport Canada |
| TRCA | Toronto Region Conservation Authority |
| TUCCN | Toronto Urban Climate Change Network |
| UNESCO | United Nations Educational, Scientific and Cultural Organization |
| UNFCCC | UN Framework Convention on Climate Change |
| WCRP | World Climate Research Program |

Acknowledgments

The Evaluation Project Team would like to thank those individuals who contributed to this project, particularly members of the Evaluation Committee as well as all interviewees who provided insights and comments crucial to this evaluation.

The Evaluation Project Team was led by Linda Lee, under the direction of the Environment Canada Evaluation Director, Shelley Borys, and included Lindsay Fitzpatrick, Karine Kisilenko, Gavin Lemieux, Katheryne O’Connor, Valeria Pandelieva and Shelley Tice.

Prepared by the Evaluation Division, Audit and Evaluation Branch

Table of Contents

EXECUTIVE SUMMARY	i

1.0	INTRODUCTION	1

2.0	BACKGROUND AND CONTEXT	1

2.1	Program Profile	3

2.1.1	Enhancement and Operation of Global and Regional Climate Models	4

2.1.2	Development of the Canadian Climate Change Scenarios Network (CCCSN)	4

2.1.3 Specialized Information on Climate Extremes and Related Hazards	5

2.2	Stakeholders and Partners	6

2.3	Governance	6

2.3.1	Program Organizational Structure	6

2.3.2	Interdepartmental Governance of the Clean Air Agenda	7

2.4	Resource Allocation	7

2.5	Program Logic Model	9

3.0	EVALUATION DESIGN	11

3.1	Purpose and Scope	11

3.2	Evaluation Approach and Methodology	11

3.3	Limitations and Challenges	12

4.0	FINDINGS	13

4.1	Relevance	13

4.1.1	Issue 1: Continued Need for the Program	14

4.1.2	Issue 2: Alignment with Government Priorities	16

4.1.3	Alignment with Federal Roles and Responsibilities	17

4.2	Performance	19

4.2.1	Achievement of Expected Outputs and Outcomes	20

4.2.2	Implementation of the Program	32

4.2.3	Demonstration of Efficiency and Economy	34

5.0	CONCLUSIONS	36

6.0	RECOMMENDATIONS	38

7.0	MANAGEMENT RESPONSE	39

Annex 1 Adaptation Theme Logic Model	43

Annex 2 Evaluation Issues and Questions	44

Annex 3 List of Background Information and Supporting Documentation	51

Annex 4 Summary of Findings	53

# EXECUTIVE SUMMARY

The evaluation of the Improved Climate Change Scenarios Program was conducted by the Evaluation Division of Environment Canada’s Audit and Evaluation Branch (AEB) in 2009–2010 to meet the information requirements of senior management and to contribute results to the thematic and Clean Air Agenda (CAA) level evaluations by the fall of 2010. This evaluation assessed the relevance and performance of the Program from 2007–2008 to 2009–2010, examining five key issues:

- Continued need for the Program;

- Alignment with government priorities;

- Alignment with federal roles and responsibilities;

- Achievement of expected outcomes; and

- Demonstration of efficiency and economy.

PROGRAM PROFILE

The Improved Climate Change Scenarios Program is one of seven programs that together comprise the Adaptation Theme of the Clean Air Agenda (CAA). The CAA is a horizontal federal strategy that represents a part of the federal government's broader efforts to address the challenges of climate change and air pollution, with a view to building a clean and healthy environment for Canadians. As part of the Adaptation Theme, the Improved Climate Change Scenarios Program is designed to facilitate changes in the behaviour of Canadians to develop and use knowledge, information, tools and collaborative arrangements in order to take appropriate actions to reduce their risks from the impacts of climate change. More specifically, the objective of the Improved Climate Change Scenarios Program is to contribute to the availability and use of improved information on the future climate, climate extremes and climate change impacts.

The Program’s activities focus on three key components: the enhancement and operation of global and regional climate models; the development of climate scenarios for climate, weather extremes and hazards; and the development of specialized information on hazards and climate extremes for infrastructure design. The first program area, climate modelling, is conducted by scientists at the Canadian Centre for Climate Modelling and Analysis (CCCma) while the other two program areas, climate change scenarios and development of information on hazards and climate extremes, are carried out by scientists in the Adaptation and Impacts Research Section (AIRS). Climate models are computer generated simulations that allow scientists to estimate climate conditions globally and regionally as well as to simulate climate change. Using these climate models, climate change scenarios define a range of possible future climate conditions to assess future hazards and extreme climate conditions that could develop as a result of climate change. This information feeds into the development of tools and information related to climate extremes that assist in disaster management planning and updating Canada’s infrastructure codes and standards to include impacts of climate change.

METHODOLOGY

Data for the evaluation were collected through a review of documents and key informant interviews. Because the implementation of the Program was in its early stages at the time of data collection and analyses, assessment of the Program’s performance focused on activities, outputs and immediate outcomes that were measureable at that time. Intermediate and final outcomes were examined for demonstration of progress towards achievement.

OVERALL FINDINGS

Evaluation findings are summarized in the following sections according to evaluation issue.

Issue 1: Continued Need for the Program

Program activities within the Improved Climate Change Scenarios Program meet climate change information needs by contributing foundational data and information for decision making. The research and related activities conducted by the CCCma, the Canadian Climate Change Scenarios Network (CCCSN) and the hazards and extremes component contribute to an understanding of climate change and its present and future impacts. Without this research, municipal and provincial partners as well as professionals in industry and those dealing with national codes and standards would have greater difficulty making informed, strategic decisions to reduce the vulnerability of Canadians to climate change impacts and extreme weather. Evaluation findings indicate that more data and information is required, however, particularly on Canada’s North as well as updated information that feeds into infrastructure design.

Issue 2: Alignment with Government Priorities

The Program’s objectives are aligned with federal government priorities through their contributions to climate change science and adaptation and impacts research. These program activities support federal commitments to address climate change issues both in Canada and internationally. As well, the objectives of the Improved Climate Change Scenarios Program are strongly aligned with the priorities of Environment Canada. Program activities in climate modelling are linked to departmental priorities to improve the knowledge and information on weather and environmental conditions to influence decision making. In addition, research on adaptation and impacts is linked to Environment Canada’s priorities to ensure that Canadians are informed of and respond appropriately to current and predicted environmental conditions.

Issue 3: Alignment with Federal Roles and Responsibilities

There is a legitimate and necessary role and responsibility for the federal government to carry out the Program. Because climate change issues are broad across regions, departments, jurisdictions and industrial sectors, there is a need for a central organization to offer consistent and quality information. It is appropriate for the federal government to fulfil this role because it is able to provide the resources, infrastructure and capacity to mobilize the scientific community and coordinate efforts for improved knowledge on climate change impacts. Although there are other programs and organizations that provide similar information and data, these are complementary to the Improved Climate Change Scenarios Program and, because of its national focus, the Program does not duplicate the activities of these other programs and organizations. Without the Program, there would be gaps in information and data on climate change impacts and climate extremes as well as an absence of national standards for infrastructure, which could ultimately expose Canadians to increased risks to their safety and security.

Issue 4: Achievement of Expected Outcomes

Despite experiencing some delays in funding and challenges in the staffing process, the Program is achieving its intended outputs and immediate outcomes. Findings indicate that the Program has also made progress in achieving its intended intermediate and long-term outcomes, although it is still too early in program implementation to observe their full achievement.

- Achievement of Expected Outputs

The Improved Climate Change Scenarios Program is achieving all of its intended outputs. Work has been completed by CCCma on improvements to the Canadian global climate model and on the development of a regional climate model. There is also evidence of the development of tools for climate change scenarios as well as updates and improvements to the Hazards websites. All three program areas have been actively involved in producing research as well as contributing to the international scientific community through their involvement in the Intergovernmental Panel on Climate Change (IPCC). There is also strong evidence that the Program has engaged partners and established or expanded their networks. However, evidence from both interviews and documents demonstrate that the Program may face challenges in meeting future data and information demands because they are limited by internal capacity. Although the demand for CCCSN hands-on training is high, the Program is limited by the number of program staff available to conduct these sessions. As well, because capacity is limited for the hazards and extremes component of the Program, it  has not been able to deliver on all of its commitments.

- Achievement of Expected Immediate Outcomes

Evidence from interviews and document review demonstrates that the Program’s partnerships and networks have contributed to increased collaboration to address climate change issues, both in Canada and internationally. The Program’s involvement in international organizations facilitated collaborative research with partners in the international scientific community and the availability and access to research and program tools as well as the knowledge and expertise provided by program officers contributed to a higher level of collaboration among external partners.

The Program has also shown progress in contributing to the increased awareness of, availability of and access to climate information through its websites, through CCCSN training sessions and through information sessions with key stakeholders on hazards and climate extremes. The increasing number of data downloads and requests from the Program’s websites from 2007 to 2009 by target audiences demonstrate increasing awareness of climate information. Positive feedback from target audiences who participated in CCCSN’s training sessions and the hazards and extremes information sessions indicate that they have increased their awareness of and access to climate information. However, they expressed concern that the Program has limited capacity in delivering these products.

- Achievement of Expected Intermediate Outcomes

The Program has shown some progress towards achieving its expected intermediate outcomes but more needs to be done. Data from interviews suggest that some of the Program’s target populations may not have sufficient scientific expertise to use the climate information available on program websites without the assistance of program staff. As well, evidence indicates that users of information find regionally or locally focussed information more useful to their work than national or global information and updated climate change data and information on climate extremes are required to support changes to codes and standards for infrastructure.

- Achievement of Expected Long-term Outcomes

Evidence indicates that there is some progress in the application of research and climate information among user groups to assess climate change risks and to plan for future climate extremes but more needs to be done, particularly in incorporating climate change risks into infrastructure designs. Overall, evidence suggests that it is too early to observe stakeholders adapting their behaviour to reduce vulnerabilities to the impacts of climate change. Similarly, it is too early to observe the reduction of risks to communities, infrastructure and the health and safety of Canadians.

- Program Delivery

Evidence suggests that the Program is generally on track to being implemented as planned but it is not clear whether or not complete implementation will take place within the Program time frame given delays in delivering on program commitments. CCCma’s work on climate modelling was delivered as planned and, while most activities were on track for CCCSN and the hazards component, CCCSN experienced delays in developing new tools for developing climate change scenarios and the hazards component was late in developing new methodologies for extreme event analyses. Data suggest that this was partly due to delays in funding and staffing issues. Because the Program is science-based and requires FTEs to produce its outputs, delays in funding had a negative affect on the Program’s ability to hire staff as planned. This difficulty in hiring scientists was compounded by the limited supply of qualified candidates and by delays in departmental staffing actions, particularly for the hazards and climate extremes component that had the largest number of positions to staff. AIRS was able to hire scientists on a contract basis but these contracts are set to end in March 2011 when Adaptation funding ends.

As well, the Program’s performance measures were neither comprehensive nor appropriate overall. The performance measurement plan that is available is not fully populated, and the performance indicators provided are difficult to measure and not specific enough to provide an adequate assessment of the Program’s performance. Some performance data are available (e.g., performance data on website use and participant evaluations from training workshops) but other than this information, there is little evidence that the Program is collecting ongoing performance data. The Program’s briefing documents to senior management provided information on progress towards planned activities or outputs, but it was difficult piecing together the full performance story because documents were not consistent across fiscal years for each program component. Part of the challenge of providing useable data for reporting and evaluation purposes may be in converting the Program’s highly technical and scientific activities and outputs into a form that is easily understandable.

A few areas for improvement in program delivery were identified by interviewees. The reach of CCCSN training sessions could be expanded given that the number of people who receive training is small compared to the number of professionals who need to be able to use the Program’s data and information. For those without the benefit of these training sessions, the websites are difficult to navigate and interviewees felt that it would be beneficial to have a more user-friendly interface as well as ongoing access to the scientific expertise of program staff to answer questions.

Issue 5: Demonstration of Efficiency and Economy

Evaluation evidence suggests the Program is employing cost-efficient measures. For example, the Program’s strategy of building in-house science capacity facilitates knowledge transfer from senior-level scientists and helps the Program to achieve its goals and expected activities at the lowest possible cost. As well, synergies are created between these program scientists and various research networks in universities and regional research groups. This enhances the internal research capacity within the Department while reducing the duplication of research and saving on some overhead costs. CCCSN training sessions are also efficient in that they reach many members of the research community at once rather than having to address individual questions by users. However, a cost-efficiency analysis was not possible because of insufficient financial information.

The economy of the Program was likewise difficult to assess. A full cost analysis comparing resources expended to the achievement of outcomes was not possible because it is too early in program implementation to observe some of the Program’s outcomes and there was a lack of clear, detailed documents outlining all program outputs and activities, their associated costs, and progress towards the achievement of intended outcomes.

CONCLUSIONS

The following conclusions on the Program’s relevance and performance have been developed based on evaluation findings and analyses:

- The Improved Climate Change Scenarios Program is relevant in meeting climate change information needs and is aligned with governmental priorities and federal roles and responsibilities.

The Program is fundamental in its provision of foundational data and information on climate change and its impacts.  Because the Program’s objectives and activities provide specialized scientific research on climate change and its impacts, its relevance is linked to the Government of Canada’s broader policy objectives and priorities related to climate change issues.  Program activities, outputs and intended outcomes are aligned with Environment Canada’s priorities to improve knowledge and information on weather and environmental conditions to influence decision-making. These data and information help to influence changes to infrastructure design that take into account present and future climate hazards and extremes, ultimately contributing to protect the safety and security of Canadians and their property.

There is a legitimate role and responsibility for the federal government to deliver this program because, without these data and information, Canada would be more vulnerable to climate change and its impacts that pose considerable threat to the health and well-being of Canadians.  This evaluation demonstrates that the federal government has a necessary role and responsibility in carrying out climate modelling, establishing and operating climate monitoring networks, conducting impacts and adaptation research in response to policy needs and providing national leadership in the direction, co-ordination, and funding of climate science in Canada.  The Government of Canada is well suited for this role because it is able to provide the large amount of scientific expertise, resources, infrastructure and capacity (including technical capacity) needed to address climate change impacts for the long-term.  Other programs and organizations involved in similar activities are complementary rather than duplicative the Program.  As well, there is a need for centralization to provide consistent information and quality data with an independent, national perspective that can contribute to the international scientific community.  Because climate change is a global phenomenon that must be addressed in concert with other countries, the Program’s research activities in the international scientific community contribute to shared knowledge and understanding of climate change and its impacts around the world.

- Current resource levels and difficulties in staffing pose a challenge for the Program in achieving its expected outcomes, particularly for the hazards and extremes component of the program.

There is a clear tension between expectations for the Program to achieve its intended outcomes and its ability to deliver on its commitments fully.  The Improved Climate Change Scenarios Program is a science-based initiative that relies on the expertise of its scientists to meet its research objectives and achieve its expected outcomes.  Adaptation funding for this program was intended to provide salary dollars for new work on climate modelling, climate change scenarios and, in particular, hazards and extremes research.  Because there were delays in receiving Adaptation funding, the Program was unable to staff positions as planned to complete the work required.  Departmental funding adjustments during the second year of implementation also had a negative impact on the Program’s ability to achieve its intended outcomes.  For example, there were delays in completing research on settlements in the North and AIRS was not able to complete on time its extreme event analyses to support the development of new national codes and standards.  The activities and intended outcomes are not considered to be realistic as originally planned given the Program’s capacity, particularly for the hazards and extremes component, which required the highest number of positions to be staffed.

- The Program could be improved by expanding its reach and providing more useful information to target audiences.

One of the Program’s strengths relating to cost-efficiencies are the synergies created with research networks in universities, regional research groups and regional Environment Canada staff in order to harness scientific expertise to achieve program objectives.  These networks and partnerships have reduced duplication of effort, saved on overhead costs and have led to greater collaboration to address climate change issues.  However, improvements could be made to the kinds of partnerships and networks possible.  For example, increased partnerships with regional organizations could lead to more joint research projects and stronger connections with other federal departments could increase communication and coordination of climate change research activities across the federal government.  As well, CCCSN training workshops and information sessions for the hazards component of the Program were generally well-received by target audiences, but key informants felt that these reach only a portion of their potential target users.  By expanding the reach of these sessions, awareness could be raised among more target users of the Program’s products (e.g., websites, research) and could facilitate their use and application of the Program’s climate change data and information.  Expanding the Program’s partnerships and networks through improved outreach activities could enhance its ability to achieve its expected outcomes.

As well, the Program could be improved by providing more useful information.  Climate change impacts are not experienced on a global scale; extreme weather events are experienced locally and adaptive strategies therefore need to be locally focused to be effective.  In particular, regionally or locally focussed information is more useful than national or global information for external partners.  The general consensus across internal and external partners, however, is that regionally focussed climate change information is generally not sufficiently available, particularly for the North given the greater rate of climate change in this area and the impact for northern communities.  As well, technical committees for developing infrastructure among external partner require updated data and information on climatic design values to support the development of new national codes and standards.  Without these updated data and information, Canadians are increasingly vulnerability to the negative impacts of climate change.

- The Program is generally being implemented as planned but the lack of ongoing performance data created difficulties in demonstrating the full performance story.

The evaluation found that the comprehensiveness and appropriateness of the Program’s performance data could be improved.  For example, a performance measurement plan for the Program was developed but this framework is not fully populated and the performance indicators that were identified lack sufficient specificity to provide useful measures of the Program’s progress towards achieving intended outcomes. Performance data were available but some of this information was highly scientific and technical such that its complexity limited its usefulness in the evaluation.  This evaluation demonstrates that, despite some delays, the Program is being implemented as planned but the lack of ongoing performance information for all program activities and outputs makes it difficult to assess the achievement of expected outcomes.

RECOMMENDATIONS

The following recommendations were developed based on evaluation findings and conclusions.  Given that the evaluation demonstrated the relevance of the Program and that program activities are on track for achieving expected outcomes, these recommendations are provided to improve on performance should decisions be made to continue the Program.  These recommendations are directed to the Assistant Deputy Minister (ADM) of the Science and Technology Branch.

Recommendation 1: Develop and implement a plan forward that considers the best utilization of the Program’s capacity when establishing priority commitments.

It is not clear that the Program will be able to deliver on all of its expected commitments, particularly for the hazards and extremes component. Available financial resources created challenges for the Program to staff as planned in order to carry out all of its planned research and research-related activities. Therefore, the Program should reconsider its expectations to deliver on all of its commitments. Prioritizing expected deliverables according to departmental needs and the needs of its stakeholders and partners might prove beneficial. Considering existing resource levels, the Program should then explore and implement ways to meet those priority commitments that would have the greatest negative impact if not delivered.

Recommendation 2: The Program should consider ways to increase their reach to target audiences and enhance their ability to meet target users’ climate change information needs, within the context of the Program’s capacity.

CCCma, CCCSN and the hazards and extremes component each have a specific target population for their climate change data and information, each with a specialized area of expertise and research interests. The general consensus among stakeholders is that the Program produces good research and its scientists are well-respected in Canada and internationally, but there was concern expressed that the Program’s climate change data and information were not reaching as large an audience as possible. The Program, therefore, should explore options to increase reach, such as expanding its partnerships and networks with regional organizations and other federal departments to facilitate increased use and application of its products for CCCma, CCCSN and the hazards and extremes component.

The Program’s target audiences have specific climate change information needs and are more likely to use data if they are useful for their needs. The general consensus among Program partners is that more climate change data and information specific to the regions are required, particularly for the North. As well, updated climatic design values are imperative for developing infrastructure that takes extreme climate conditions into account. The Program, therefore, should explore viable options of how to expand its research and related activities to include more climate change data and information that meet these needs. The Program may also consider consulting with stakeholders and partners to identify other key data and information required by target users in order to increase their usefulness further.

Recommendation 3: Develop a performance measurement framework that includes a clear strategy for ongoing data collection for reporting.

While program objectives were clearly identified in program documents, a clear strategy for measuring progress towards achieving these objectives was not as evident. A performance measurement plan was available but it was not fully populated and performance indicators were not sufficient to provide accurate, ongoing measures of the Program’s progress towards achieving outputs and intended outcomes. Therefore, the Program should ensure that a complete performance measurement strategy is developed and implemented that includes specific, measurable performance indicators with specific targets and timelines for measuring progress. When developing these indicators, the Program should explore ways to translate its complex, scientific data into useful information for reporting so that the full meaning of the output being measured is not lost. The Program should also develop a formal mechanism (e.g., a management information system) that organizes these performance measures together, including ongoing financial information, and data collection should be coordinated to ensure that ongoing performance measurement facilitates departmental reporting and future evaluation of the Program’s performance.

MANAGEMENT RESPONSE

The ADM of the Science and Technology Branch accepts the evaluation and all of its recommendations.  Provided the Improved Climate Change Scenarios Program and associated funding is renewed, the following management actions have been developed in response to these recommendations to improve on activities related to climate modeling, climate change scenarios and hazards and extremes research.

| Recommendation 1 |
| --- |
| Develop and implement a plan forward that considers the best utilization of the Program’s capacity when establishing priority commitments. |
| Statement of Agreement / Disagreement |
| Management agrees with the recommendation. |
| Management Action |
| The evaluation showed that the Program is, by and large, on track to being implemented as planned; however, in order to allow completion of work on hazards and extremes that was delayed at the outset, the Program plans to meet all of its remaining priorities by seeking program renewal beyond March 31, 2011 given that the evaluation has confirmed the relevance of the program. A plan for priority commitments will be established, wherein commitments will focus on the continuation of climate model development and further increases to the resolution of regional climate model projections to meet target audiences’ information needs. Priorities will be provision of climate data and information to specific regions, including the North, bridging and translation of new climate science on scenarios, hazards and extremes into relevant and accessible data products and tools for decision-makers, and continuation of partnerships to complete program deliverables on hazards for disaster management and infrastructure codes and standards. As part of this process, the Program will also consult with other sections within Environment Canada on cross-cutting activities that could be included in the plan forward under renewed funding. In addition, this consultation will address the broader issue of how best the federal government can facilitate the uptake and application of climate and adaptation science by target populations. Should the Program not be renewed beyond March 31, 2011 the Program will continue to focus on its current priorities, taking into account the Program’s current capacity, from now until March 31, 2011. |
| Timeline | Deliverable(s) | Responsible Party |
| March 31, 2011 | Assessment of Program’s current capacity and delivery of priority commitments. | Director General, ASTD |
| Within one year of commencement of new funding (pending future funding decisions) | A plan for addressing priority commitments under renewed funding. Evidence of consultations within Environment Canada (e.g., meeting minutes, memos, briefing notes). | Director General ASTD |

| Recommendation 2 |
| --- |
| The Program should consider ways to increase their reach to target audiences and enhance their ability to meet target users’ climate change information needs, within the context of the Program’s capacity. |
| Statement of Agreement / Disagreement |
| Management agrees with the recommendation as a suitable expectation for a renewed Adaptation program. |
| Management Action |
| The Program will continue to monitor stakeholder and partner information needs, and consider ways to increase its reach to target audiences and enhance its ability to meet target users’ climate information needs. These may include investing more heavily in delivery mechanisms, such as improved and more comprehensive provision of climate change information and supporting scientific data via web sites that have improved user interfaces, and by strategic implementation of user training workshops to reach target populations ready and capable of assimilating the information. It is important to note, however, that, to date, targeted stakeholder consultations with codes and standards agencies and provincial disaster management agencies have been completed. Training sessions on the use of climate change scenarios also continue to take place across Canada, including sessions provided upon request to stakeholders. In addition, over the coming months the new regional climate model will be in a position to provide more detailed region-specific information for all Canadians. Working within the broader EC community, will ensure that programs are developed to meet information and training needs of target populations, taking into consideration both resource and staffing issues. It would not be realistic to expand Program activities to increase its reach to target audiences and enhance its ability to meet target users’ climate change information needs without renewed funding. |
| Timeline | Deliverable(s) | Responsible Party |
| March 31, 2011 | Consultations with stakeholders and partners about information needs. | Director, CRD Director General, ASTD |
| Within one year of commencement of new funding (pending future funding decisions) | Co-lead the development of an intra-interdepartmental strategic plan for improved client service through participation in meetings and decision-making processes. Improved delivery and accessibility of outputs to enhance user up-take of information in target populations. | Director, Climate Research Division, ASTD |

| Recommendation 3 |
| --- |
| Develop a performance measurement framework that includes a clear strategy for ongoing data collection for reporting. |
| Statement of Agreement / Disagreement |
| Management agrees with the recommendation as a suitable expectation for a renewed Adaptation program. |
| Management Action |
| On April 1st, 2010 the Department instituted a new Performance Measurement Framework (PMF) which includes detailed performance measurement reporting for both outcomes and outputs. The 2010/11 PMF outlines targets at the Output, Expected Result, and Strategic Outcome levels. At the Strategic Outcome, Expected Result and Output levels performance indicators have been identified for the hazards and extremes components of the Program e.g.: science input to new infrastructure / building codes, and climate projections and climate data sets on various time and spatial scales. These indicators are in line with the recommendations from the 2006 report by the Office of the Auditor General (CESD). At the Output level, a performance indicator for the climate modelling and projections component has also been identified. Accordingly, the data collection needed to report on these PMF indicators is now integrated within this overarching Departmental structure. Should the Program be renewed, it will seek additional opportunities and mechanisms to meet the near and longer term information needs of target populations, particularly in the context of climate service delivery, to which the Program would be an important contributor. The Program will carefully consider how to measure the performance of climate scientific research programs in a manner that takes into consideration the fact that the impacts of this research often take many years to manifest, and are dependent upon the capacity and abilities of target populations to assimilate. Therefore performance measurement strategies must focus on longer term performance measures dependent on capacity of target populations to change behaviour, and not solely individual programs. |
| Timeline | Deliverable(s) | Responsible Party |
| Completed | PMF for 2010/11. | WES Board Secretariat |
| March 31, 2011 | Fully populated PMF for 2010/11 for the Output, Expected Result, Evidence of continued data collection and reporting under the recently adopted PMF (e.g., web use statistics, surveys, stakeholder evaluations). | Director, CRD |
| Within one year of commencement of new funding (pending future funding decisions) | The Program will develop a performance measurement framework encompassing longer time frames, in the context of Canadian adaptive capacity. | Director General, ASTD |

# 1.0	INTRODUCTION

An evaluation of the Improved Climate Change Scenarios Program was conducted in 2009–2010 by Environment Canada’s Evaluation Division, Audit and Evaluation Branch (AEB). This program was identified for evaluation as part of AEB’s Three-Year Risk-Based Audit and Evaluation Plan for 2009–2012, approved by the Departmental Evaluation Committee (DEC) on May 22, 2009.

The objective of this evaluation was to assess the Program’s relevance and performance, covering a three-year time frame from 2007–2008 to 2009–2010. This evaluation was conducted to meet the information requirements of senior management and to fulfil Treasury Board Secretariat requirements. Results from this program evaluation will also contribute to the evaluation of the Adaptation Theme of the Clean Air Agenda (CAA). The Improved Climate Change Scenarios Program is one of seven programs included in the CAA Adaptation Theme. Evaluations of each of these seven programs, including the Improved Climate Change Scenarios Program, will be rolled up to provide an Adaptation-Theme-level assessment of federal efforts related to adaptation to the impacts of climate change. This theme-level assessment is required to inform decision making at the CAA level.

This document presents the findings and recommendations of the Evaluation of the Improved Climate Change Scenarios Program and is organized in the following way. Section 2.0 provides background information on the Program. Section 3.0 presents the evaluation design, including the purpose and scope of the evaluation, as well as the methods used to conduct the evaluation. Section 4.0 presents the evaluation’s findings. Section 5.0 and 6.0 lay out, respectively, the conclusions and recommendations. The management response is presented in Section 7.0.

# 2.0	BACKGROUND AND CONTEXT

The Improved Climate Change Scenarios Program is one of seven programs that comprise the Adaptation Theme of the Clean Air Agenda (CAA). The CAA is a horizontal federal strategy that represents a part of the federal government's broader efforts to address the challenges of climate change and air pollution, with a view to building a clean and healthy environment for Canadians. To support federal efforts in delivering the CAA, a total of $1.7 billion was allocated between 2007–2008 and 2010–2011. The CAA involves more than 40 programs, delivered by nine federal departments and agencies, which are organized into the following eight themes:

- Clean Air Regulations;

- Clean Transportation;

- Clean Energy;

- Management and Accountability;

- Indoor Air Quality;

- Community Partnerships;

- International Actions; and

- Adaptation.

As noted previously, the Improved Climate Change Scenarios Program is part of the Adaptation Theme. Unlike other themes of the CAA which focus on initiatives to reduce greenhouse gas (GHG) emissions (known as mitigation measures), initiatives under the Adaptation Theme are designed to assist Canadians to alter their behaviour in ways that reduce the negative impacts of climate change. According to the fourth assessment report (2007) of the Intergovernmental Panel on Climate Change (IPCC), the additive effects of both mitigation and adaptation can significantly reduce the risks of climate change impacts. Taken alone, neither adaptation nor mitigation can prevent significant climate change impacts; “[m]itigation is necessary to reduce the rate and magnitude of climate change, while adaptation is essential to reduce the damages from climate change that cannot be avoided.” While mitigation activities are carried out in programs within other themes of the CAA, the Adaptation Theme specifically supports adaptive activities in response to climate change impacts.

The CAA Adaptation Theme groups together seven programs that are designed to assist Canadians in developing and using knowledge, information, tools and collaborative arrangements in order to take appropriate actions to reduce their risks from the impacts of climate change. All programs within the Adaptation Theme are intended to contribute to the achievement of two long-term outcomes: 1) improving Canada’s capacity to reduce health risks arising from air pollution and a changing climate; and, 2) improving Canada’s capacity to adapt and respond to a changing climate and air pollution. Resources were also targeted to address three urgent risks related to:

- the North, where climate change impacts are already very visible, vulnerability of communities and infrastructure is high and the federal government has constitutional and land claim obligations to Aboriginal people;

- human health, as it is affected by changing climate conditions and the spread of infectious diseases; and

- infrastructure, to ensure that the government and industry infrastructure that is developed over the coming decades is designed to endure changing future climate conditions.

As part of the CAA Adaptation Theme, the Improved Climate Change Scenarios Program addresses the risk related to Canada’s infrastructure by providing foundational scientific research on climate change impacts and by working with national commissions and associations involved in setting building standards that take into consideration climate change impacts in their infrastructure design.

Evaluations of each of the seven programs within the Adaptation Theme were conducted in 2009–2010, and results from these program-level evaluations will be rolled up to the Adaptation Theme level in mid-2010. Results from the thematic evaluation will then be aggregated together with those from the other thematic evaluations within the CAA in the fall of 2010.

## 2.1	Program Profile

The Improved Climate Change Scenarios Program is a science-based program within Environment Canada that is intended to contribute towards improved information on climate change and its impacts. With increasing evidence indicating that the climate is changing and will continue to change in the foreseeable future, information and predictive tools developed through the Program are intended to contribute to decision making within Canada in order to be able to reduce and respond to potential risks associated with climate change and facilitate increased adaptive behaviour.

The Program’s activities focus on three key components:

- the enhancement and operation of global and regional climate models;

- the development of climate scenarios for climate, weather extremes and hazards; and

- the development of specialized information on hazards and climate extremes for infrastructure design.

Climate models are computer-generated simulations that allow scientists to estimate climate conditions globally and regionally as well as simulating climate change. Using information generated from climate models, climate change scenarios define a range of possible future climate conditions to assess climate change impacts like weather hazards and climate extremes. In order to facilitate adaptive behaviour, tools and information related to climate extremes are developed by the Program to assist stakeholders to develop and implement proactive and preventative measures in disaster management planning and to update Canada’s infrastructure codes and standards that take into account climate change impacts.

The first program activity, climate modelling, is conducted by scientists at the Canadian Centre for Climate Modelling and Analysis (CCCma). The other two program activities, climate change scenarios and development of information on hazards and climate extremes, are part of the research on climate change impacts and adaptation and are carried out by scientists in the Adaptation and Impacts Research Section (AIRS). Both CCCma and AIRS are aligned under the Climate Research Division (CRD) in the Atmospheric Science and Technology Directorate (ASTD) of the Science and Technology Branch at Environment Canada. Because the specialized science involved in climate modelling is different from the specialized science involved in climate change impacts and adaptation research, there is little ongoing interaction or shared activities between CCCma and AIRS. There are, however, more opportunities for connections within AIRS between scientists examining climate change scenarios and those studying weather hazards and climate extremes. (Refer to Section 2.3.1 on Program Organizational Structure for fuller discussion.)

Each of the three program activities is presented in more detail in the following sections.

### Enhancement and Operation of Global and Regional Climate Models

The first set of activities of the Improved Climate Change Scenarios Program involves the enhancement and application of Canada’s global and regional climate models by scientists at CCCma.

Program activities focus on:

- developing computer models of the climate system to simulate global climate, regional climate and climate change; and

- analyzing past and predicted climate variations to gain a deeper understanding of the climate system.

The global climate system involves large-scale, dynamic, physical interactions among the Earth’s atmosphere, biosphere, oceans, land surfaces and ice cover that respond to varying levels of greenhouse gases (GHGs) and aerosols. In order to examine the Earth’s climate and the effect of these pollutants, scientists have developed climate models, which are complex mathematical representations of the Earth’s climate which can capture a comprehensive view of future climate change. These climate models simulate climate variations over a three-dimensional spatial area and over a specific time period, factoring in varying levels of air pollutants to allow scientists to simulate historical climate change. They can provide projections of global climate or regional climate. Regional climate models (RCMs) cover only a limited area but have higher resolution than the global model, thus providing a means of “zooming in” on a particular part of the world to provide more detailed data for a smaller area. With advances in computer technology and improved understanding of the earth’s climate system, increasingly sophisticated climate models have been developed over the years that permit studies of more complex climate questions.

As part of the Improved Climate Change Scenarios Program, CCCma’s research activities focus on developing, analyzing, testing and operating more advanced versions of the Canadian global model  to provide more robust simulations that better represent future climate conditions. CCCma is also involved in the development of a new regional climate model that produces climate change information at a finer spatial scale. Output from these climate models is distributed through the CCCma website for use by the scientific community. These data are intended to help inform decision makers across all levels of government and in industry, and ultimately the Canadian public, about future climate change and its uncertainties.

### 2.1.2	Development of the Canadian Climate Change Scenarios Network (CCCSN)

The second set of activities of the Improved Climate Change program involves the development of the Canadian Climate Change Scenarios Network (CCCSN) and the development of climate change scenarios for climate, weather extremes and hazards. Originally launched in 2005, the objectives of CCCSN are:

- to support climate change impact and adaptation research in Canada and internationally;

- to support stakeholders requiring scenario information for decision making and policy development;

- to provide access to Canadian research on the development of scenarios and adaptation research, including work produced by AIRS.

Climate change scenarios, derived from global climate models, define a range of possible climate conditions extending about 100 years into the future and allow scientists to examine the impacts of climate change. When developing climate change scenarios, scientists combine and compare the information from multiple global models developed internationally, including the Canadian global climate model. Since these climate change scenarios play an important role in assessing future hazards, they are used by research and decision-making communities in adaptation and climate change impacts studies to inform planning and decision making to respond to climate change risks.

At AIRS, the CCCSN functions on two levels: as a social network of working teams of climate change scenarios researchers; and as a physical network of locations in each region in Canada, as well as the Arctic. The latter, called “nodes,” each house computer servers to carry out scenario research. All of these nodes have been set up with supercomputing capacity, but the Arctic node has only recently begun to operate and the Atlantic and Pacific nodes are not yet running. Housed in major universities and colleges within each region, the CCCSN facilitates the sharing of regionally relevant research on adaptation and climate change impacts developed at each node. Research in the regional nodes is carried out by Environment Canada employees and university partner scientists, and is coordinated by the CCCSN manager to minimize duplication and maximize the usefulness of the research produced. The information produced by the scenario network is made accessible to the public through hands-on training workshops and through the CCCSN website.

### 2.1.3 Specialized Information on Climate Extremes and Related Hazards

The third set of activities of the Improved Climate Change program involves developing specialized information on climate extremes and related hazards. In the coming years, the frequency and intensity of climate-related hazards and severe weather events are expected to increase substantially as a result of climate change. Tools and information related to climate extremes, therefore, are required to help the implementation of proactive and preventative measures in local disaster management planning and in updating Canada’s infrastructure codes and standards.

Program activities include:

- enhancing methodologies for risk assessment using existing climate information, trends and scenarios information;

- developing methodologies for incorporating climate change impacts into infrastructure design; and

- disseminating hazards information to end users through the Canadian Atmospheric Hazards Network website.

The program activities for developing information on hazards and extremes include consultations with multiple stakeholders, usually via committees that represent industry, academia, provinces, territories, municipalities, professional engineering organizations and other decision makers. These consultations include discussions on procedures to incorporate climate change information into existing codes, standards, guidelines and practices, as well as participation in national committees and commissions that are involved in making adjustments to the design of Canada’s infrastructure. By including this climate extremes and impacts information into the decision-making process, the goal is to make Canada’s infrastructure more resilient and better adapted to more frequent extreme weather and climatic events.

Hazards information is disseminated to end users through the Canadian Atmospheric Hazards Network website, which provides hazards information related to all regions of Canada that focuses specifically on climate change and climate extremes. The Hazards Network is aimed at providing tools and information to support disaster risk planning and emergency preparedness within municipal and provincial governments. Collaboration and consultations are undertaken with provincial and municipal emergency management representatives to facilitate this process.

## Stakeholders and Partners

The Improved Climate Change Scenarios Program involves engagement with a number of stakeholder groups and partners:

- Internal partners (e.g., Meteorological Service Canada [MSC]);

- Other federal departments (e.g., NRCan, DFO);

- Provincial and municipal governments;

- Canadian and International scientists involved in climate modelling;

- Canadian and international scientists involved in climate change scenario development;

- Universities;

- Research organizations (e.g., National Roundtable on the Environment and the Economy (NRTEE), Ontario Centre for Climate Impacts and Adaptation Resources (OCCIAR));

- Emergency preparedness and disaster risk planners; and

- Professional and industry associations and commissions (e.g., Canadian Standards Association (CSA), Canadian Commission on Fire and Building Codes (CCBFC), Transportation Association of Canada).

## Governance

Because the Improved Climate Change Scenarios Program is one of the seven programs under the Adaptation Theme of the CAA, its governance and accountabilities, insofar as they relate to the CAA, are tied to existing structures under the CAA architecture. The following sections describe the Program’s organizational structure within Environment Canada and its governance as part of the CAA.

## Program Organizational Structure

The Improved Climate Change Scenarios Program is housed within the Climate Research Division (CRD) in the Atmospheric Science and Technology Directorate (ASTD) of Environment Canada’s Science and Technology Branch. Program activities are organized separately within two sections of CRD according to area of specialization: the Canadian Centre for Climate Modelling and Analysis (CCCma) carries out climate modelling activities and the Adaptation and Impacts Research Section (AIRS) conducts research on climate change scenarios and on hazards and extremes. Because CCCma scientists and AIRS scientists are involved in different streams of research and because most CCCma scientists and AIRS scientists are not physically located together, there is little ongoing interaction across the two sections.

At the outset of this evaluation, AIRS was a division (called the Adaptation and Impacts Research Division [AIRD]) and became subsumed as a section under CRD in November 2009. As a result of this change, financial information is now reported together for CCCma and AIRS under CRD and the reporting structures for the climate change scenarios and the climate extremes and hazards activities shifted. While CCCma and AIRS activities were aligned in different sub-activities in Environment Canada’s departmental structure prior to this change, they will be aligned together under the new 2010–2011 Program Activity Architecture (PAA) that is used for departmental planning and reporting purposes. These organizational changes will have an effect on the roles and responsibilities within AIRS and CRD but the full impact was not clear at the time of the present evaluation.

## Interdepartmental Governance of the Clean Air Agenda

The Improved Climate Change Scenarios Program reports through Environment Canada’s governance structures and is also accountable to existing governance structures at the Adaptation Theme and horizontal CAA levels. The CAA is a horizontal initiative that has implemented the CAA Horizontal Management Accountability and Reporting Framework (HMARF) to facilitate coordination across CAA themes. The accountability structure for the HMARF is composed of senior-level interdepartmental committees that are responsible for providing strategic direction, coordination, and managerial oversight of the CAA.

A Director General Management Committee (DGMC) for each of the eight themes under the CAA is intended to provide guidance at the thematic level. Although the Chair of the DGMC is typically a Director General (DG) within the lead department, the DGMC chair for the Adaptation Theme rotates every two years among the DGs responsible for the programs under this theme. DGMC meetings are called quarterly and the DG of the Improved Climate Change Scenarios Program (or his or her representative) attends this meeting to contribute to discussion of issues at the theme level and to provide updates on program activities as required.

## 2.4	Resource Allocation

Funding for the Improved Climate Change Scenarios Program is unlike the other programs under the Adaptation Theme in that it provides incremental funding for new work among existing research activities that include climate modelling, climate change scenarios development and specialized information on extremes and hazards. As presented in Table 1, a total of $15M of CAA funding and 34 FTEs were allocated across these three components within the Improved Climate Change Scenarios Program over a three-year period starting in 2008–2009. Salary dollars account for approximately 50–60% of total funds for each program component and all FTEs funded through this theme for the extremes and hazards component are new positions (except for core support and services). This Adaptation funding was intended to account for approximately 30%, of both O&M and salary dollars, of the total funding for CRD each year for 2008–2009 and 2009–2010.

Table 1: Resource Allocation for the Improved Climate Change Scenarios Programa by Program Component for 2007–2008 to 2010–2011

|  | Climate Modelling | Climate Change Scenarios | Extremes and Hazards | Total |
| --- | --- | --- | --- | --- |
|  | FTEsa | 16.5 (incl. 4 new) | 6.5 (incl. 3 new) | 11 (incl. 10 new) | 34 |
| 2007–2008 | Salaries ($M) | 0 | 0 | 0 | 0 |
|  | O&M ($M) | 0 | 0 | 0 | 0 |
|  | TOTAL ($M) | 0 | 0 | 0 | 0 |
| 2008–2009 | Salaries ($M) | 1.348 | 0.537 | 0.910 | 2.736 |
|  | O&M ($M) | 0.923 | 0.262 | 1.229 | 2.415 |
|  | TOTAL ($M) | 2.272 | 0.799 | 2.139 | 5.211 |
| 2009–2010 | Salaries ($M) | 1.491 | 0.397 | 0.985 | 2.873 |
|  | O&M ($M) | 1.034 | 0.185 | 0.808 | 2.027 |
|  | TOTAL ($M) | 2.526 | 0.582 | 1.792 | 4.900 |
| 2010–2011 | Salaries ($M) | 1.490 | 0.358 | 0.953 | 2.801 |
|  | O&M ($M) | 1.016 | 0.177 | 0.896 | 2.088 |
|  | TOTAL ($M) | 2.506 | 0.535 | 1.849 | 4.889 |
| TOTAL | Salaries ($M) | 4.329 | 1.293 | 2.848 | 8.470 |
|  | O&M ($M) | 2.974 | 0.624 | 2.933 | 6.530 |
|  | Total ($M) | 7.303 | 1.916 | 5.780 | 15.0 |

a No Grants and Contributions are associated with this program.

b Includes Core Support Service (0.5 to 1.5 FTE per year)

Although Improved Climate Change Scenarios is a four-year program, funds were requested for only the last three years. As shown in Table 1, no funds were requested as part of the CAA Adaptation Theme for the Program’s first year of implementation in 2007–2008. During this time, funds from the Climate Change Interim Strategy (CCIS) were to cover program activities which would then be funded through the Adaptation Theme in subsequent years. However, a series of confounding factors created financial pressures that affected the Program’s ability to deliver its commitments on time:

- In 2007–2008, the Program did not receive CCIS funding when this funding was not specifically allocated to departmental programs;

- In 2008–2009, O&M dollars were reduced for both CCCma and AIRS when adjustments were made by the Department to offset the impact of the sunsetting of the CCIS; and

- Adaptation funding that was to cover expenses for climate modelling activities and research on adaptation and impacts was received six months later than expected in 2008–2009 (in September), creating additional financial pressures for the Program.

  - This delay was a function of the roll-out of the CAA program; the entire CAA had been approved a year in advance but the Adaptation Theme was added later to the CAA, and there was a lag time before approvals and funding could be allocated to programs.

As a result of these circumstances, ASTD could not deliver on all of its CCCma and AIRS commitments. (Refer to Section 4.2.2 on Implementation of the Program for fuller discussion of impacts.)

## 2.5	Program Logic Model

The Adaptation Theme Logic Model was developed as part of the planning phase of the Adaptation Theme evaluation. Extensive consultations were held with all programs involved in the Adaptation Theme in order to ensure that all participating departments agree that the resulting thematic logic model best represents all programs within the theme and makes the appropriate connections to CAA-level outcomes. (Refer to Annex 1 for Adaptation Theme Logic Model.)

The program-level logic model for the Improved Climate Change Scenarios Program is based on this theme-level logic model and was also developed as part of the planning phase of the Adaptation Theme evaluation. At the outset of the evaluation, further refinements were made to this logic model in agreement with the Program to ensure program-level activities, outputs and outcomes are accurately presented while still maintaining the connections to the thematic and CAA levels.

The following logic model in Figure 1 provides a visual display of program activities, outputs and outcomes for the Improved Climate Change Scenarios Program.

# 3.0	EVALUATION DESIGN

## 3.1	Purpose and Scope

This evaluation assessed the relevance and performance of the Improved Climate Change Scenarios Program from 2007–2008 to 2009–2010 to provide information to senior management for decision making and to provide results for the Adaptation Theme evaluation to be rolled-up to the CAA-level in the fall of 2010. Five key issues were examined, as presented in the Evaluation Matrix in Annex 2:

- Continued need for the program;

- Alignment with government priorities;

- Alignment with federal roles and responsibilities;

- Achievement of expected outcomes; and

- Demonstration of efficiency and economy.

Research and associated program activities that were to be resourced through the incremental funding for the Improved Climate Change Scenarios Program under the Adaptation Theme were assessed as part of this evaluation. Data were collected from August through October 2009, with some follow-up interviews conducted in November 2009 to capture the impact of organizational changes within ASTD that occurred after the first phase of the evaluation had already been completed. Additional documents were requested throughout the analysis and reporting phases of the evaluation to fill gaps in data and to capture information on the Program’s ongoing progress towards the achievement of expected outcomes. Because the implementation of the Improved Climate Change Scenarios Program was in its early stages at the time of data collection and analyses, assessment of the Program’s performance focused on activities, outputs and immediate outcomes that were measurable at that time. Longer-term outcomes (intermediate and final outcomes) were examined for demonstration of progress towards their achievement.

## 3.2	Evaluation Approach and Methodology

    - Methods

Data were collected through a review of documents and key informant interviews to address all evaluation issues described in the Evaluation Matrix in Annex 2.

Document Review – The Program was requested to provide program documents to demonstrate its relevance and performance. The evaluation team reviewed key documents including Speeches from the Throne, federal budgets, Reports on Plans and Priorities (RPPs), Departmental Performance Reports (DPRs), peer reviewed research papers and presentations, planning documents, commissioned reports, documents related to stakeholder consultations and meetings, financial information and quantitative data from participant evaluations of training sessions. (A complete list of documents reviewed is presented in Annex 3.)  Evaluators reviewed these documents and compiled data in a source document which was then analyzed in order to address each evaluation question.

Key Informant Interviews – A total of 50 key stakeholders were interviewed from the following groups:

- Senior departmental and program management (9);

- Internal departmental program partners (6);

- Other federal departments (9);

- Municipal, Provincial and Territorial governments (4);

- Universities (6);

- Research communities, institutions and organizations (6);

- National committees, associations and commissions (4);

- Resource managers, emergency preparedness and risk planners (4); and

- International partners and stakeholders (2).

All names and contact information for interviewees were provided by the Program. Semi-structured interviews were conducted in the interviewee’s language of choice, using an interview guide tailored for each category of key informant. Interviews were conducted either in person or by phone.

## 3.3	Limitations and Challenges

There were some limitations and challenges to this evaluation.

Implementation of the Program is in its early stages

This evaluation was scheduled to take place in the third year of the Program’s implementation in order for results to be available in time for a roll-up to the thematic and CAA levels. Due to funding issues involving CCIS and delays in receiving Adaptation Theme resources, however, program activities could not fully begin until approximately one year prior to the launch of this evaluation. In effect, the Program was in place for less than one year when the evaluation began. As such, evidence was not available to assess progress toward all intended program outcomes.

Re-structuring of program occurred mid-evaluation

Changes in the organizational structure of the Program occurred midway through the evaluation. The Adaptation and Impacts Research Section (AIRS), previously Adaptation and Impacts Research Division (AIRD), was subsumed under the Climate Research Division (CRD). Because AIRD was a division, it operated under its own budget and reported directly to the Director General of ASTD. Because this change occurred after the data collection for the evaluation was completed, follow-up interviews were conducted with key program managers and senior managers to obtain evidence on the potential impacts of this change. Most of the data collected through interviews, however, reflect the Program prior to this change in organization.

Attribution of expected outcomes to program is difficult

It was difficult to connect the achievement of expected outcomes to Improved Climate Change Scenarios activities due to three confounding factors. First, climate research has a long history in the Department, making it difficult to attribute the achievement of outcomes directly to program activities and outputs that occurred within the time period examined through the evaluation. Second, the incremental funding for the Improved Climate Change Scenarios Program obtained under the Adaptation Theme was intended to support additional research and its related activities, particularly staffing actions. As a result, it was difficult to attribute the achievement of expected outcomes solely to those activities funded under this theme. Third, the research produced as part of the Improved Climate Change Scenarios Program necessarily requires an iterative process that involves input from multiple sources to test findings and develop solid conclusions. As such, the achievement of expected outcomes relies not only on the Improved Climate Change Scenarios Program but on research activities from the wider scientific community upon which the Improved Climate Change Scenarios Program relies.

Because of this difficulty in attribution, emphasis was placed on the contribution of activities and outputs to the achievement of expected outcomes rather than on attributing observed results to the Program

# 4.0	FINDINGS

This section presents the findings for each evaluation issue (i.e., relevance and performance) and its related evaluation questions. (Refer to Annex 2 for the Evaluation Matrix.) The findings at the overall issue level are presented first, followed by the findings for each evaluation question.

A rating is also provided for each evaluation question based on evaluation findings. The rating symbols and their significance are outlined below in Table 2. A summary of ratings for the evaluation issues and questions is presented in Annex 4.

Table 2: Rating Symbols and Significance

| Symbol | Significance |
| --- | --- |
| Achieved | The intended outcomes or goals have been achieved or met |
| Progress Made, Attention Needed | Considerable progress has been made to meet the intended outcomes or goals, but attention is still needed |
| Little Progress, Priority for Attention | Little progress has been made to meet the intended outcomes or goals and attention is needed on a priority basis |
| Too early to observe achievement | Program is on track but it is too early in program implementation to observe achievement of expected outcome |
| N/A | A rating is not applicable |
| ~ | Outcomes achievement ratings are based solely on subjective evidence |

## 4.1	Relevance

Evaluation Issue: Relevance

Overall Findings: Program activities within the Improved Climate Change Scenarios Program meet climate change information needs by contributing foundational data and information for decision making. The research and related activities conducted by CCCma, CCCSN and the hazards and extremes component contribute to an understanding of climate change and its present and future impacts. Without this research, municipal and provincial partners as well as professionals in industry and those dealing with national codes and standards would have difficulty making informed, strategic decisions to reduce the vulnerability of Canadians to climate change impacts and extreme weather. Evaluation findings indicate that there is an ongoing need for data and information, particularly on Canada’s North as well as in providing updated information to feed into infrastructure design. The Program’s objectives are aligned with federal government priorities through their contributions to climate change science and adaptation and impacts research. These program activities support federal commitments to address climate change issues both in Canada and internationally. As well, the objectives of the Improved Climate Change Scenarios Program are strongly aligned with the priorities of Environment Canada. Program activities in climate modelling are linked to departmental priorities to improve the knowledge and information on weather and environmental conditions so as to influence decision making. Research on adaptation and impacts helps to ensure that Canadians are informed of and respond appropriately to current and predicted environmental conditions. There is also a legitimate and necessary role and responsibility for the federal government to carry out the Program. Because climate change issues are broad, cutting across regions, departments, jurisdictions and industrial sectors, there is a need for a central organization to provide leadership in offering consistent and quality information. The federal government is well suited for this role because it is able to provide the resources, infrastructure and capacity to mobilize the scientific community and coordinate efforts for improved knowledge on climate change impacts. Although there are other programs and organizations that provide similar information and data, these are complementary to the Improved Climate Change Scenarios Program. Thus, the Program does not duplicate the activities of these other programs and organizations because of its national focus. Without the Program, there would be gaps in information and data on climate change impacts and climate extremes as well as an absence of national standards for infrastructure, which could ultimately expose Canadians to increased risks to their safety and security.

### 4.1.1	Issue 1: Continued Need for the Program

| Issue 1: Continued Need For the Program | Indicator(s) | Methods | Rating |
| --- | --- | --- | --- |
| Are activities within the Program connected with key environmental climate change needs? | Degree to which the Improved Climate Change Scenarios Program continues to meet climate change adaptation needs | Document review Key informant interviews | Achieved |

Research activities within the Improved Climate Change Scenarios Program are connected with key environmental climate change needs.

- The impacts of climate change are already evident through global warming, increases in the number, duration and intensity of heat waves and heavy precipitation events, changing precipitation patterns and river flows, and melting Arctic sea ice and permafrost, all of which will have significant implications for Canada’s communities and infrastructure. For example, longer and more intense heat waves and smog events increase the potential for adverse effects on health, while coastal erosion from rising sea levels, more severe winter storms and more frequent flash floods pose greater risks to safety and property.,

- The literature identifies the need for Canada to develop a co-ordinated process to prioritize climate change risks and plan for adaptation in response to these climate change impacts, noting the need for the types of research developed through the Improved Climate Change Scenarios Program such as analyses of the impacts of climate change as well as climate science activities like climate modelling.

- Program documentation demonstrates consistency between program activities and meeting these climate change information needs. For example, peer-reviewed publications and working papers by program scientists address information gaps and identify areas of potential risk to infrastructure and public safety. As well, climate science information produced by the Program through its climate modelling activities and research on adaptation and impacts are made available through the development and maintenance of the CCCma, CCCSN and hazards websites.

- Key informants report that the Program’s research activities contribute foundational data and information for decision making. In their view, this helps to reduce the increased vulnerability of Canadians and Canadian communities over the long term due to climate change and extreme weather, particularly in terms of existing infrastructure.

- Interviewees report that the Program contributes to meeting climate change needs by providing access to data and information via program websites and training sessions.

      - External partners identified a dependence on climate modelling and adaptation and impacts research in order to perform their own work (e.g., academics, other researchers and scientists, engineers, municipal planners). As well, interviewees report that having a Canadian climate model run by Canadian scientists helps to develop scientific capacity domestically and also gives Canada a leading role within the international scientific community; and

      - Partnerships and networks established through the Program’s activities are viewed as contributing greatly to the larger climate science community, particularly in the ways that these links feed other organizations like Ouranos, the National Research Council (NRC) and the Canadian Standards Association (CSA).

- Evidence from interviews, however, also identifies some program shortfalls in terms of meeting climate change needs. For example, program products (e.g., website tools) are viewed as being underutilized, although the reason for this is unclear; climate modelling and data on Canada’s North are inadequate; and information that feeds into infrastructure design needs to be updated to account for climate change.

### 4.1.2	Issue 2: Alignment with Government Priorities

| Issue 2: Alignment with Government Priorities | Indicator(s) | Methods | Rating |
| --- | --- | --- | --- |
| Are activities within the Program aligned with federal government priorities? | Degree of alignment between the objectives of the Improved Climate Change Scenarios Program and federal government priorities related to adaptation to climate change | Document review Key informant interviews | Achieved |

The objectives of the Improved Climate Change Scenarios Program are aligned with larger federal government priorities through their contributions to climate change science and to adaptation and impacts research.

- The Government of Canada priorities outlined in the 2007 and 2008 Speeches from the Throne and 2007 Budget identify the federal government’s commitment to addressing climate change issues. While the 2009 Speech from the Throne does not refer specifically to adaptation or climate change, it does commit to building Canada through new investments in infrastructure as part of its economic stimulus plan.

  - Evidence from both program documentation and interviews indicates that the Program has actively participated in consultations with national organizations that form and publish the National Building Code of Canada (NBCC) to update codes and standards to include more recent climatic information for extreme weather resilience for new and retrofitted infrastructure.

- As well, Canada is a signatory to the UN Framework Convention on Climate Change (UNFCCC) which legally commits all parties to formulate, implement, publish and update adaptation measures. According to interviewees, the Program provides the climate science as well as adaptation and impacts research from which these adaptation measures may develop. As well, the Program supports federal international commitments through its research contributions to the IPCC Fourth Assessment Report. The Program was working to contribute scientific climate research to the IPCC Fifth Assessment Report at the time of data collection.

| Issue 2: Alignment with Government Priorities | Indicator(s) | Methods | Rating |
| --- | --- | --- | --- |
| Are activities within the Program aligned with the priorities of Environment Canada? | Extent to which the objectives of the Improved Climate Change Scenarios Program match mandate and priorities of Environment Canada Perceptions regarding the degree of alignment and examples of alignment between priorities of Environment Canada and the Improved Climate Change Scenarios Program | Document review Key informant interviews | Achieved |

There is evidence that the objectives of the Improved Climate Change Scenarios Program are strongly aligned with Environment Canada priorities.

- Evidence from program documents demonstrate that program activities, outputs and intended outcomes are aligned with Environment Canada’s Departmental Strategic Outcome that Weather and environmental predictions and services reduce risks and contribute to the well-being of Canadians. More specifically,

  - CCCma’s program activities in the development and enhancement of global and regional climate models provide scientific climate information to contribute to the departmental priority to improve knowledge and information on weather and environmental conditions to influence decision making; and

  - AIRS’ research activities on adaptation and climate change impacts address the departmental priority to ensure that Canadians are informed of, and respond appropriately to, current and predicted environmental conditions. AIRS’ adaptation science plan, which describes its mission, strategic directions and implementation and measurement strategies, clearly describes the alignment between its activities and this departmental priority and how AIRS contributes to the larger scientific research agenda for the Department.

- The majority of key informants felt that the Program is aligned to a great extent with departmental priorities but some felt adaptation should be an even greater priority for the Department.

### 4.1.3	Alignment with Federal Roles and Responsibilities

| Issue 3: Alignment with Federal Roles and Responsibilities | Indicator(s) | Methods | Rating |
| --- | --- | --- | --- |
| Is there a legitimate and necessary role and responsibility for the federal government in the Improved Climate Change Scenarios Program? | Absence/presence of similar programs within the federal and/or provincial governments Extent to which similar programs complement or duplicate the Improved Climate Change Scenarios Program Perceptions and examples of gaps in meeting the climate change needs of Canadians without the Program | Document review Key informant interviews | Achieved |

Evaluation evidence demonstrates that there is a legitimate and necessary role and responsibility for the federal government to deliver the Program as it provides a unique service, is well positioned to overcome jurisdictional boundaries so that necessary information can be provided at a national and regional level, and is a trusted source of the information. The Improved Climate Change Scenarios Program complements other similar programs, providing information and services that are unique within the climate change science network and contribute to the success of complementary programs.

    - Interviewees felt that the Government of Canada has a responsibility to ensure the safety and security of Canadians from threats of environmental harm (including climate change impacts on infrastructure) as well as negative impacts on the economy. The federal government is believed to be well suited for this role because it is able to provide the large amount of scientific expertise, resources, infrastructure and capacity (including technical capacity) needed to address climate change impacts in the long term. As well, there is a need for centralization to provide consistent information and quality data from an independent, national perspective that can contribute to the international scientific community.

- Evidence from documents supports this view. The 2006 Report of the Commissioner of the Environment and Sustainable Development (CESD) contends that the federal government has a necessary role and responsibility in carrying out climate modelling, establishing and operating climate monitoring networks, conducting impacts and adaptation research in response to policy needs and providing national leadership in the direction, co-ordination, and funding of climate science in Canada.

- In addition, NRTEE recommends that the federal government dedicate resources to reliably update and disseminate regionally relevant climate data and information, climate change projections and climatic design values to support infrastructure decisions. NRTEE further notes that there are many implications for Canada’s North related to monitoring capacity and that there has been a reduction in federal involvement in developing and updating climatic design values. The report also notes the reluctance of organizations that develop and update Codes, Standards and Risk Instruments (CSRIs) to use climatic design values derived by any group except Environment Canada, which they perceive as an expert, reliable, neutral third party.

- Interviewees generally viewed other programs and organizations involved in the same or similar activities (for example, the Pacific Climate Impacts Consortium (PCIC) in B.C. and the North American Regional Climate Change Assessment Program (NARCCAP) in the U.S.) as being complementary rather than duplicating the Improved Climate Change Scenarios Program. Reasons provided included observed differences in activities between the Program and these other programs or groups; the national focus of the Program compared to the regional focus of other research organizations; and the need for research to build on or duplicate previous analyses to ensure the robustness of results (e.g., most scientists will encourage the use of multiple models in climate science research because of the uncertainty inherent in each model’s design). One interviewee, however, suggested that there could be a better division of labour between the federal government and regional organizations with regard to the work being done.

- Interviewees also felt that, in the absence of the Program, there would be gaps in available information both in Canada and internationally, lack of consistent or national coverage that focuses on broad issues, and an absence of national standards for infrastructure which would result in a high degree of liability for organizations. Interviewees felt that these gaps would lead to loss of awareness, knowledge and expertise in the scientific community as well as an increase in property damage, lost productivity and negative impacts on the safety and security of Canadians.

- Interviewees generally felt that there is no one ready or able at this point to fill any gaps that would arise should the Program cease to function, contending that Environment Canada is the only organization with the capacity, expertise and mandate to address adaptation needs on behalf of Canada and Canadians. The reasons given focused on areas such as the large amount of investment, resources and/or capacity required; the time required to put things in place (e.g., software infrastructure); and the regional focus of some other organizations involved in this area. The challenge in obtaining Canada-specific information from international sources was also mentioned.

## Performance

Evaluation Issue: Performance

Overall Findings: The Improved Climate Change Scenarios Program is achieving all of its intended outputs. Work has been completed by CCCma on improvements to the Canadian global climate model and on the development of a regional climate model. There is also evidence of the development of tools for climate change scenarios as well as updates and improvements to the Hazards websites. All three program areas have been actively involved in producing research and the Program has engaged partners and established or expanded their networks. There may be some challenges in meeting future data and information demands, however, because the Program is limited by internal capacity. Evidence from interviews and document review demonstrates that the Program’s partnerships and networks have contributed to the immediate outcome of there being increased collaboration to address climate change issues, both in Canada and internationally. However, more needs to be done to help increase awareness of, availability of, and access to climate information through the Program’s websites, through CCCSN training sessions, and through information sessions with key stakeholders on hazards and climate extremes. Although the demand for the CCCSN hands-on training is high, the Program is limited by the number of program staff available to conduct these sessions. As well, the capacity of the hazards and extremes component of the Program is limited, resulting in the Program’s inability to deliver on all of its commitments. For expected intermediate and long-term outcomes, the Program has shown some progress but more needs to be done. It is generally too early in program implementation to observe full achievement, particularly in terms of incorporating climate change risks into infrastructure design. Regarding increased use of program products, data from interviews suggest that some of the Program’s target populations may not have sufficient scientific expertise to use the climate information available on program websites without the assistance of program staff. As well, evidence indicates that users of information find regionally or locally focussed information more useful to their work than national or global information. Evidence suggests that the Program is generally on track to being implemented as planned, but it is not clear whether or not complete implementation will take place within the Program timeframe given delays in delivering on program commitments. Data suggest that the Program experienced some difficulty in hiring scientists to conduct hazards and climate extremes research and delays in funding created difficulties for the Program to deliver on all of its objectives. Overall, the Program’s performance measures were neither comprehensive nor appropriate. Some ongoing performance data are available (e.g., performance data on website use and participant evaluations from training workshops) but other than this information, there is little evidence to demonstrate that ongoing performance data are being collected. The Program’s briefing documents to senior management provided information on progress towards planned activities or outputs, but it was difficult piecing together the full performance story because documents were not consistent across fiscal years for each program component. Part of the challenge in providing ongoing performance information for reporting and evaluation purposes may be in converting the Program’s highly technical and scientific activities and outputs into a form that is easily understandable. A few areas for improvement in program delivery were identified by interviewees. The reach of CCCSN training sessions could be expanded given that the number of people who receive training is small compared to the number of professionals who need training in order to use the Program’s data and information. For those without the benefit of these training sessions, the websites are difficult to navigate and interviewees felt that it would be beneficial to have a more user-friendly interface as well as ongoing access to the scientific expertise of program staff to answer questions.

### Achievement of Expected Outputs and Outcomes

The following sections (4.2.1.1 to 4.2.1.4) describe the evidence and ratings for the achievement of expected outputs and outcomes for the Improved Climate Change Scenarios Program.

#### Achievement of Expected Outputs

| Issue 4: Achievement of Expected Outcomes | Indicator(s) | Methods | Rating |
| --- | --- | --- | --- |
| 5a) To what extent have intended outputs been achieved within the Program? |
| Tools, Processes and Systems | Evidence of enhanced global climate model and development of regional climate models Evidence of development of tools for climate change scenarios Evidence of updates to scenarios and hazards websites | Document review Key informant interviews | Achieved |
| Research | Number of peer-reviewed publications Program outputs in international assessments Evidence of the development of new research based on new climate models Evidence of methodologies examined for incorporating changing climate into infrastructure design | Document review Key informant interviews | Achieved |
| iii) Partnerships and Networks | Evidence of participation in research networks or committees Number of CCCSN servers deployed by region and by location Number of CCCSN training workshops conducted Number of regional sites added to hazards website Evidence of stakeholder organizations consulted | Document review Key informant interviews | Achieved |

#### 4.2.1.1.1	Tools, Processes and Systems

Evidence from document review and interviews indicate that the Program is producing its intended tools, processes and systems for each of the components of the Improved Climate Change Scenarios Program, although some deliverables for the hazards and extremes component were not evident at the time of data collection.

- For program outputs in climate model development, evidence demonstrates that extensive work has been completed on the development of and improvements to, climate models. For example, CCCma is carrying out tests for Canada’s new Earth System Model (Can ESM2), is making improvements to other climate models such as a Canadian Terrestrial Ecosystem Model (CTEM) and the Canadian Model of Ocean Carbon (CMOC), and has conducted numerous experiments on regional climate models in collaboration with university partners and consortiums. While internal partners and stakeholders agree that the Program is achieving its outputs for global and regional climate models, other government departments feel that climate information for the North is lacking and requires special attention.

- Evaluation findings also demonstrate evidence of the development of tools for climate change scenarios. Key informants noted that the Program is providing ongoing data updates and identified the development of software tools for mapping and an online tool for developing bio-climate profiles on the CCCSN website that facilitate access to climate information. The 2009–2010 mid-year review for AIRS notes that the Program is on track for making intended improvements to the network’s website and for developing new scenario validation methods with Canadian academics and international partners.

  - Documents also reveal that updates and improvements have been made to the Hazards website that have included additional images, maps and data on snow, floods, heat and cold. Briefing documents for senior management suggest the Program is on track but most program staff and some internal partners felt that the evaluation was taking place too early to be able to state conclusively that the hazards and extremes component was achieving its intended outputs. Nevertheless, they did agree that it was progressing adequately.

#### 4.2.1.1.2	Research

Evidence clearly shows that research is being produced by each of the areas within the Improved Climate Change Scenarios Program.

  - A total of 157 peer-reviewed publications were published by CCCma and AIRS between 2007 and 2009. The number of publications by program area is presented in Table 3.

Table 3: Number of publications by Section

|  | Number of Peer-Reviewed Publicationsa |
| --- | --- |
| CCCma | 45 |
| AIRS b | 112 |
| TOTAL | 157 |

a Peer-reviewed publications include journal articles, books, book chapters, reports and occasional papers.

b Data on publications were provided for AIRS as a whole and could not be separated by CCCSN and Hazards research.

- As well as producing research for publication, scientists from both CCCma and AIRS contribute to the international scientific community through their ongoing participation in IPCC assessment reports. Both internal and external partners indicate that published research on climate models by CCCma scientists contributed to the generalized conclusions reported in the IPCC assessments and view this as a strength of the Program. Documentation supports this finding, demonstrating that the CCCma global climate model was used to generate climate change scenarios for the 2007 IPCC Fourth Assessment Report.

  - In addition to contributing to the international scientific community through involvement in the IPCC, the Program conducts research to expand knowledge and understanding of climate change. Interviews with program staff indicate that experiments have been conducted on the Canadian global climate model and that papers based on this research have been submitted or published. This is supported through documents that provide evidence of experiments and model runs for further enhancements of Canada’s global climate model. Furthermore, documents show that CCCma’s Canadian global climate models are among the top ranking models within the field.,

- Program staff and external partners report that the development of enhanced methodologies for incorporating changing climate into infrastructure design is in progress. Program documents also demonstrate that research and development of proposed codes and standards are being carried out for the 2010 National Building Code. A 2009–2010 mid-year review for AIRS, however, notes that delays in staffing led to delays in the development of new models and methodologies for analyses of extreme wind and flood events. Delays in research related to settlements in the North were also experienced, although no reasons for this delay were provided. In contrast, the development of new analytical approaches for climate change, infrastructure and transportation in southern Canada is reported to be on track.

#### Partnerships and Networks

There is strong evidence that the Program has engaged partners and established or expanded their networks, although some challenges were identified.

- Evidence from both interviews and program documents show that the Program participates in formal research networks (e.g., Global Ocean-Atmosphere Prediction and Predictability [GOAPP] Network), engages with partners on research projects (e.g., with academics, for Canadian Stratospheric Processes and their Role in Climate [C-SPARC] and Canadian Network for Regional Climate Modelling and Diagnostics [CRCMD]) and serves on advisory or steering committees or task forces (e.g., for Pacific Climate Impacts Consortium [PCIC], Climate Change Task Force for the Transportation Association of Canada, National Building Code of Canada’s [NBCC] Climatic Loads Task Group).

- For research on climate change scenarios, the development of research partnerships is facilitated through the CCCSN. CCCSN nodes are groups of “working teams” based at different physical locations with super-computer capacity to conduct climate change research. Plans were to establish six regional nodes (Pacific, Yukon, Prairie, Ontario, Quebec and Atlantic nodes), each with hardware (computer servers) and access to data as well as funding to develop regional expertise and research. Interviews with program staff and briefing documents to senior management indicate that the Program is on track to increasing the number of regional nodes as planned. Program staff reports that servers have been deployed to all regional nodes except for the Pacific and Atlantic nodes. Regional research was in progress but websites were not yet functional, although the Program reported being on schedule for finalizing the websites and providing public access to them.

- CCCSN also conducted training sessions where participants learn about what is available on the CCCSN website and how climate change information can be displayed, downloaded, validated and interpreted using tools available on the CCCSN website. Evidence shows that the CCCSN conducted eight regional training sessions that were carried out in Toronto, Regina, Fredericton and Whitehorse within the scope of this evaluation. Only two sessions had been planned, but additional sessions were added (using AIRS O&M funds) at the request of CCCSN website users. Key informants felt that these sessions were a good opportunity for scientists with common information goals to network with one another.

- For the Hazards network, the Ontario, Atlantic and Prairie and Northern nodes of the Canadian Atmospheric Hazards network were running at the time of data collection, while the Pacific and Yukon as well as Quebec nodes were still waiting release. These three nodes were established during the analysis and reporting phase of the evaluation so that the national Hazards network is now complete.

- Data from both interviews and documents also provide evidence that  partnerships and networks for the work on hazards and extremes have been expanded through consultations that were held with stakeholder organizations. For example, consultations were completed with the Conservation Authorities (CAs) of Ontario, the Transportation Association of Canada, the Arctic Council, and the Canadian Telecommunications Preparedness Emergency Association.

- Formalized agreements are another mechanism to facilitate collaboration. At the time of data collection, one formal Memorandum of Understanding (MOU) had been established between the Program and with CSA to work together on developing standards and codes but interview data suggest that other formalized partnerships are in development.

- Some key informants, however, believe that the Program’s ability to increase and expand their partnerships and networks may be limited.

  - Program staff feel that they need more FTEs with relevant subject matter expertise to manage data and information requests from partners and stakeholders. The demand is extensive but the supply of scientists with relevant expertise who can provide this service is limited. The Canadian Meteorological and Oceanographic Society (CMAO) estimates that, taking into account all government, private sector and academic employment, there are approximately 1200 people across Canada with some atmospheric science background. This creates additional pressures when staffing because the pool of qualified candidates is small. The Program has expanded its search internationally, with some success, to draw expertise back into Canada.

  - According to external interviewees, academics that were once part of the CCCma research community are no longer able to participate due to funding cuts from federal organizations such as National Sciences and Engineering Research Council (NSERC). This factor is external to the Program but points to the vulnerability of the Program in terms of accessing expertise.

  - One regional partner felt that, although the connections that do exist are likely good, there are some gaps in the kinds of partnerships and networks that could be developed through the CCCSN. For example, CCCSN could improve on their partnerships with other federal departments (such as NRCan) so as to improve communication and coordination of research activities.

#### Achievement of Expected Immediate Outcomes

| Issue 4: Achievement of Expected Outcomes | Indicator(s) | Methods | Rating |
| --- | --- | --- | --- |
| 5b) To what extent have immediate outcomes been achieved within the Program? |
| i) Increased awareness of, availability of and access to research, websites and climate models | Number of data downloads and data requests from program websites Evidence of increased awareness of, availability of and access to global and regional climate models Evidence of increased awareness and improved knowledge on climate models among training sessions and workshop participants Evidence of improved access to hazards websites | Document review Key informant interviews File review | Progress made, attention needed |
| ii) Greater collaboration within Canada and internationally to address climate change issues | Evidence of collaboration with key stakeholders and program partners, as demonstrated by: Co-authored publications Formal agreements Engagement with standards and codes agencies and industry associations | Document review Key informant interviews | Achieved |

4.2.1.2.1	Increased awareness of, availability of and access to research, websites and climate models

Data suggest that there has been some progress in increased awareness of, availability of and access to models, websites and research among the users of the Program’s products. However, continuous work is needed to increase the reach of users.

- Program staff feel that there is increasing awareness of, availability of and access to program outputs, as demonstrated by the increasing number of data downloads and data requests for each of the Program’s websites. The Program collects ongoing performance data on website usage for the CCCma, CCCSN and Hazards websites. A review of program files on website usage indicates that the number of data downloads for CCCma and the number of data requests for CCCSN and the Hazards websites has increased since 2007, with the exception of CCCma, which showed a 20% decline in data downloads between 2007 and 2008. (Please refer to Table 4 for distribution across years for each program component.) These observed increases suggest that target users were aware of program websites and the available information, and were able to access the data.

Table 4: Number of Data Downloads and Data Requests by Year

|  | 2007 | 2008 | 2009 | Total |
| --- | --- | --- | --- | --- |
| CCCma website a | 14,854 | 11,858 | 15,952 | 38,785 |
| CCCSN website b | 787,296 | 1,372,335 | 2,185,445 | 4,345,076 |
| Hazards website b | 264,135 | 866,669 | 1,041,691 | 2,172,495 |
| TOTAL | 1,066,285 | 2,250,862 | 3,243,088 | 6,560,235 |

a Number of data downloads by users.

b Number of data requests by users.

- Program staff feel that they have increased their target audience’s awareness of and access to Canada’s global climate model and the regional climate models. They report that they have achieved this through their research, the results of which are made available through publications, presentations and posting on the CCCma website for viewing and downloading. Internal and external partners who work with CCCma also agree with this view, noting that CCCma has helped improve their knowledge of models by providing expert advice, publishing peer-reviewed research and presenting at conferences and workshops. Some interviewees note, however, that the highly technical and specialized nature of this climate model information creates challenges in making this information useful for decision-making.

- This increased awareness is also evident through the training sessions that were conducted by CCCSN officers. These hands-on, regional training sessions were conducted across Canada to train participants on the use of CCCSN products, such as climate change scenarios data, as well as to promote availability and access to the hazards and climate extremes information on the Hazards website. Participant evaluations of a series of training workshops held during the course of this evaluation show that strong majorities of participants rated the overall workshops (89%) and their content (83.5%) as “very good” or “excellent”, and felt the AIRS instructors were very helpful, approachable and knowledgeable, with a great deal of subject matter expertise. Some interviewees, however, expressed concern that CCCSN was restricted by the number of program staff available to conduct these sessions and answer questions posted by users on the CCCSN website,  which may be a limiting factor in the Program’s performance.

- This limited capacity was also identified for the hazards and extremes component of the Program. Although interviewees generally felt that the Program has contributed to increased awareness of, availability of and access to climate extremes research and hazards information through the Program’s ongoing information sessions with key stakeholders and partners, external partners suggest that technical committees for developing infrastructure do not have updated data and information on climatic design values because the data that feed into these values are not available. This lack of data is corroborated by evidence from the Program’s progress report to senior management that indicates extreme event analyses to support the development of new national codes and standards have been delayed. These delays are attributed to staffing issues. At the time of interview, only 2 of the 12 FTEs positions were staffed to carry out activities on hazards and extremes. This lack of data could have a serious impact on the ability of target users to make informed decisions on infrastructure designs, which could ultimately have a negative impact on the safety of Canadians.

4.2.1.2.2	Greater collaboration within Canada and internationally to address climate change issues

Overall, the Program’s established partnerships and networks led to greater collaboration to address climate change issues.

- This evaluation examined how the Program’s partnerships and networks contributed to observed increases in collaboration with key stakeholders and partners to address climate change issues. As observed by some interviewees, collaboration to address climate change issues may not be solely attributed to the Program because there is a long history of climate modelling and climate science in Canada and research organizations in this field have existed for a long time. Professional collaboration may have been well established prior to the beginning of the Program and some of this collaboration may result from personal networks and informal contacts within the scientific community rather than directly linked to program outputs.

- Overall, increased collaboration as a result of the Program’s established partnerships and networks was demonstrated in the following ways:

  - The Program’s involvement in international organizations such as IPCC and the North American Regional Climate Change Assessment Program (NARCCAP) facilitated collaborative research with partners in the international scientific community. Program staff and internal partners feel that this involvement in international committees and projects has resulted in increased awareness, recognition, influence and respect for Canadian climate modelling and research on adaptation and climate change impacts within the international scientific community.

  - Engagement with agencies, groups and consortiums working on climate impact and adaptation issues has also facilitated collaboration. Interviews with program staff and external partners demonstrate that the Program’s partnerships with industry and professional associations have resulted in collaboration among partners and contributed to building safe infrastructure.

- Interview data also indicate that collaboration among key stakeholders and programs was initiated or expanded further as a result of the Improved Climate Change Scenarios Program activities and outputs. External partners note that availability and access to the research and tools produced by the Program as well as knowledge and expertise provided by program officers contributed to the higher level of collaboration they experienced with their own stakeholders in their own work.

#### Achievement of Expected Intermediate Outcomes

| Issue 4: Achievement of Expected Outcomes | Indicator(s) | Methods | Rating |
| --- | --- | --- | --- |
| 5c) To what extent have intermediate outcomes been achieved within the Program? |
| i) Increased use of websites and climate models among target populations | Perceptions among target populations on use of climate models and program websites in their own work | Document review Key informant interviews | Progress made, attention needed |
| ii) Increased capacity to conduct climate change impacts and adaptation research among target populations | Demonstrated evidence of increased capacity to conduct climate change impacts and adaptation research as a result of the Program | Key informant interviews Document review | Progress made, attention needed |
| iii) Increased application of adaptation science and climate change research among target populations and appropriate jurisdictions | Demonstrated evidence that adaptation and climate change impacts research has been applied | Key informant interviews Document review | Progress made, attention needed |

        - Increased use of websites and climate models among target populations

It is not clear from the evidence how data and information accessed from Program websites are being used. Potential users may not have the capacity to use this information and the usefulness of the information available may be improved with more focus on regional or local climate data.

- Program records indicate that the Program’s websites are being increasingly accessed over the last two years. (Refer to Table 4 for frequency of data access for each program component.) However, while access to data and information on Program websites increased, it is difficult to determine how it is being used. External partners report that, with the exception of climate science experts, data and information available on these sites may be difficult for some target populations (e.g., industry and other levels of government) to use without assistance from program staff. Similarly, interviews suggest that not all potential users of the Program’s products are equipped to use them and require this information to be available in a useable form. As a consequence, while scientific researchers reportedly access and make use of the data, other target groups with less technical or scientific capacity (e.g., municipalities) seek out information from other sources.

- The level of use of climate change data and information may also vary according to their perceived usefulness. Evidence demonstrates that external partners are more likely to find regionally or locally focussed information more useful to their work than national or global information. For example, respondents to a survey on community access and use of climate information, were much more likely to rate regional or local climate projections than national or global climate projections as “very useful” (77% versus 23%, respectively). This finding is consistent with evidence from interviews with external partners, who reported that there was a greater use of information from climate change networks with a regional or local focus (e.g., PCIC, the Toronto Urban Climate Change Network).

4.2.1.3.2	Increased capacity to conduct climate change impacts and adaptation research among target populations

Evidence indicates that progress is being made towards increased capacity for target groups to conduct climate change impacts and adaptation research, but more needs to be done.

- As for increased use of websites and climate models, increased capacity for target populations to conduct climate change impacts and adaptation research largely depends on the target group. Interviewees report that availability of downscaled models and training sessions to improve access to the websites that were provided by the Program has contributed to increased capacity among scientists to conduct their own climate change impacts and adaptation research. Documentation demonstrates that community leaders still require the expertise of program officers to use and apply specialized climate information as well as to understand this information in a broader context when developing strategies to reduce vulnerability to climate change.  However, the degree to which the department is responsible for the capacity building of target users is not clear.

- External factors that affect the capacity of target populations to conduct their own research revolve around available resources. External partners noted that the lack of officers with sufficient expertise and the limited financial resources within their own organizations impedes their capacity to utilize climate information and to conduct adaptation and impacts research. As well, the instability of federal funding from other sources such as the Canadian Foundation for Climate and Atmospheric Science (CFCAS) negatively affects the capacity of climate modelling scientists to conduct their research.

4.2.1.3.3	Increased application of adaptation science and climate change research among target populations and appropriate jurisdictions

Although there is some evidence demonstrating that target groups have applied adaptation and climate change research in their own work, it is too early to determine whether or not this outcome has been fully achieved.

- Almost half of key informants report that it is too early to assess whether or not this outcome has been achieved, suggesting that research may be applied more fully over the next 5 to 10 years to improve Canada’s infrastructure design to account for climate change impacts. Documents, however, suggest that this application of research has begun. A 2009 survey finds that 61% of communities report the Program’s climate information is useable for their purposes but there are still only a few communities making use of this information. For example, cities like Ottawa, Toronto and Vancouver have used adaptation and impacts research for planning purposes at the local level (e.g., for work on freezing rain and sea walls).

- While the Program has worked towards making information available and teaching target groups how to access and use the data, interviewees feel there is still limited application of this research in Canada. Overall, interviewees note that there needs to be more work on raising awareness of the impacts of climate change and educating Canadians on the need to adapt before adaptation science and climate change research can be applied. Increased awareness of and education on scenarios information and climate science research are a foundational contribution that will lead to application.

#### Achievement of Long-Term Outcomes

| Issue 4: Achievement of Expected Outcomes | Indicator(s) | Methods | Rating |
| --- | --- | --- | --- |
| 5d) To what extent have long-term outcomes been achieved within the Program? |
| i) User groups apply tools and information to assess climate change risks and plan adaptation strategies | Opinions among user groups that research and related products from the Program were used to assess risk and inform the development of strategies and plans to prepare for future climate extremes Evidence of the adoption of new building codes that consider climate change risks | Document review Key informant interviews | Too early to observe achievement |
| ii) Stakeholders have taken actions to reduce their vulnerabilities from, and have adapted to, predicted impacts of climate change | Perceptions that behaviours have changed as a result of the Program Examples of user groups that factor climate change risks into their planning/decision processes | Document review Key informant interviews | Too early to observe achievement |
| iii) Risks to communities, infrastructure and to the health and safety of Canadians resulting from climate change have been reduced | Evidence of whether risks to the health of Canadians resulting from climate change have been reduced as a result of the Improved Climate Change Scenarios Program | Document review Key informant interviews | Too early to observe achievement |

4.2.1.4.1	User groups apply tools and information to assess climate change risks and plan adaptation strategies

Evidence suggests that the Program is generally on track to achieve this long-term outcome but it is too early to expect to observe the full achievement of this outcome.

- Progress is being made in the application of research and climate information among user groups to assess climate change risks and inform the development of adaptation strategies to plan for future climate extremes. For example, 84% of communities in a 2009 survey reported that they were developing strategic plans to adapt to climate change and the Toronto Region Conservation Authority (TRCA) is working with climate information to better plan and prepare for future climate variability.

- Interviewees generally felt that progress is being made among user groups in adopting new building codes that consider climate change risks. For example, interviewees report taking intense rainfalls into account when redesigning the drainage of roads in order to adapt infrastructure to the impacts of climate change, and the Canadian Standards Association (CSA) has used CCCSN data, among other data sources, to draft guidelines on infrastructure foundations for permafrost in Canada’s North. As well, the Toronto Region Conservation Authority (TRCA) indicates that it has been working with Environment Canada, several municipalities and multiple conservation groups on a pilot study to integrate climate change impacts into water-related infrastructure design practices. Interviewees, however, generally felt that more needed to be done to incorporate climate change risks into infrastructure designs.

4.2.1.4.2	Stakeholders have taken actions to reduce their vulnerabilities from, and have adapted to, predicted impacts of climate change

Evidence suggests that it is too early to expect to observe the full achievement of this outcome but there is some evidence demonstrating that the Program has contributed to adaptive behaviour.

- Overall, interviewees felt that it is too early in program implementation to observe adaptive behaviour to reduce vulnerabilities to the impacts of climate change. Some interviewees, however, do identify a link between the Program and observed adaptive behaviour, although some connections are stronger than others. Regional and municipal partners in both government and industry report that the Program’s work has contributed to stakeholders taking actions to reduce their vulnerability to climate change impacts (e.g., promoting personal emergency kits to prepare for major blackouts, developing an extreme heat program, making changes to regional operations to address increased risk for wildfires).

4.2.1.4.3	Risks to communities, infrastructure and to the health and safety of Canadians resulting from climate change have been reduced

Evidence suggests that the Program is generally on track to reduce risks to communities, infrastructure and to the health and safety of Canadians resulting from climate change but it is too early to tell the extent to which this outcome has been achieved.

- Interviewees, including program staff as well as internal and external partners, felt that some progress has been made and/or the Program is on track to achieve this intended outcome but were unable to report definitively that risks have been reduced. Although a few examples were provided by interviewees, they related more closely to awareness of risks than to risk reduction. In addition, the extent to which these examples could be linked to work done by the Program during the timeframe covered by the evaluation was not clear.

- Some documents indicate that codes, standards and guides are being developed nationally but documentation was generally quite limited in identifying the risks that have been reduced.

### Implementation of the Program

| Issue 4: Achievement of Expected Outcomes | Indicator(s) | Methods | Rating |
| --- | --- | --- | --- |
| Has the Program been implemented, or is it on track to being implemented, as planned? Are program activities, processes and governance structures adequate for achieving expected program results? | Extent to which performance data is comprehensive and appropriate Proportion of activities and outputs planned versus those completed Perceived adequacy of activities, processes and governance structures for achieving expected program results among program staff and partners Extent to which barriers to program implementation are identified and/or resolved | Document review Key informant interviews | Progress made, attention needed |

Program documents reveal that the Program is generally being implemented as planned but it is not clear whether or not complete implementation will take place within the Program timeframe, given the incomplete performance data available and given the delays experienced by CCCSN and the hazards and extremes component.

- Overall, the Program’s performance measures were neither comprehensive nor appropriate. Of the performance data that were available, some were well-maintained and up to date (e.g., number of data downloads and requests for data and information from program websites, evaluations from CCCSN training sessions) while most were not well-organized or useful. Part of the challenge may be in converting the Program’s highly technical and scientific activities and outputs into a form that is easily understandable for reporting and evaluation purposes. Program information was provided when requested but there was no clear indication that the Program was collecting performance information on an ongoing basis. Although a performance measurement plan for the Program is available, its performance indicators are difficult to measure, are not specific enough to provide an adequate assessment of the Program’s performance and do not include target values or baseline information. Some mid-year reviews and periodic briefings to senior management provided information on the Program’s progress but these documents were not consistently provided for each fiscal year and for each program component, and these limitations in performance information made it difficult to conduct a full comparison of planned versus actual activities or outputs to assess program implementation.

- Reporting and briefing documents, however, indicate that the Program was implemented as planned for CCCma while CCCSN and research on hazards and extremes experienced a few delays. Program documents for CCCma demonstrate that work on developing Canada’s new global climate model was completed and a new model for regional climate predictions was developed and being tested, as planned. While most activities were on track for CCCSN and Hazards in 2009–2010, CCCSN experienced delays in developing new statistical downscaling models and the hazards component was late in developing new models or methodologies for extreme event analyses. “Staffing issues” were identified in mid-year reviews to senior management and by program staff as the source of these delays. According to program staff as well as some external partners, CCCSN and the hazards and extremes component were under-resourced to carry out their activities.

- Interviewees generally expressed frustration with departmental processes that created barriers or challenges in carrying out their planned activities within the Program.

  - Funding allocation: Program staff noted that delays in receiving Adaptation Theme funding created additional difficulties for the Program to deliver on all of its objectives. Staffing actions did not proceed as quickly as planned.  As a result, there was slow progress on improvements to the Canadian global climate model for CCCma, with no progress on regional modelling. Moreover, AIRS could not complete its development of new statistical models and tools and the regional nodes were not in place as planned. Some program staff expressed the desire to have A-Base stability for AIRS to avoid similar financial pressures in the future.

  - Staffing processes: The Program experienced some difficulty in hiring the scientists required to conduct adaptation and impacts research. This was reported by program staff as being partly due to the limited supply of qualified candidates and partly due to delays in the staffing process. When a qualified scientist was identified for the position, the candidate accepted another offer, in some cases, while waiting for the staffing action to be finalized. Program staff also expressed concern that applying generalized skill requirements typically used to search for qualified candidates created challenges when staffing for the specialized skills and experience required for the job. The hazards and extremes component, which had the largest number of available positions, was able to staff most of their positions but only on contracts that will terminate once funding ends in March 2011. Program staff note that this lack of permanence has created anxiety among these scientists and many are looking for employment opportunities elsewhere.

- These issues have left the hazards and extremes component of the Program under-resourced compared to what had been planned, which could impact the Program’s progress towards achieving expected outcomes. Because Adaptation funds were largely directed towards hazards and extremes research, this component of the Improved Climate Change Scenarios Program were more affected compared to CCCma and CCCSN. To risk manage, AIRS has used casual and contract arrangements to hire and retain personnel to continue work on Program deliverables. From September 2008 through January 2010, 13 positions were staffed on term contracts that are all scheduled to expire by March 2011.

- Interviewees identify a few areas for improvement, primarily concerning client service and program delivery:

- Reach of training sessions: Interviewees felt that the number of people that receive CCCSN training is small compared to the number of professionals who need to be able to use program information and data. It was suggested that using a shorter, more introductory course for the training (similar to the training provided through Projections in Practice Program (PiP) in the UK) would broaden the reach of these training sessions.

- Accessibility of website information for clients and partners without climate science expertise: Some interviewees felt that awareness generally increases following training sessions but workshop participants do not necessarily know how to use the information fully. For those without the benefit of CCCSN training sessions, the websites are difficult to navigate and a more user-friendly interface would help target users overcome difficulties in accessing the complex, highly scientific data.

- Resources for client support, in general: External partners felt that, while appreciated, existing resources for client support are not sufficient. Although they acknowledged the challenges in providing assistance to clients, interviewees felt that they would benefit from increased access to the scientific expertise among program staff to supplement the information they find on program websites.

### Demonstration of Efficiency and Economy

| Issue 5: Demonstration of Efficiency | Indicator(s) | Methods | Rating |
| --- | --- | --- | --- |
| Is the Program undertaking its activities and delivering its outputs at the lowest possible cost? How could the cost-efficiency of the Program’s activities be improved? Are there alternative, more cost-efficient means of achieving program outputs? | Cost analysis of resource utilization in relation to the production of outputs Opinions of stakeholders on the cost-efficiency of delivering program outputs and how it could be improved | Document review Key informant interviews Review of financial information | Progress made, attention needed |

Evidence demonstrates that the Program is employing cost-efficient means to achieve its outputs but financial information was not available to assess cost-efficiency.

- The evaluation was unable to produce a veritable cost-efficiency analysis because sufficiently detailed financial information was not available for each program output across each program component.

- However, the 2008–2009 Clean Air Agenda Horizontal Performance Report provides higher level financial information up to 2008–2009.

  - No funds were requested for 2007–2008 because program activities were supposed to be funded through the Climate Change Interim Strategy (CCIS) for the first year of the Program.

  - For 2008–2009, the level of funding spent is approximately 68% less than the amounts allocated. Interview data and available documentation show that program spending was less than the budgeted amount because funding was received later in the year than expected. This resulted in delays in staffing actions, which resulted in fewer dollars spent in salary and O&M overhead costs for new staff.

- Although it was not possible to draw firm conclusions on the Program’s cost efficiency, available information from documentation and key informant interviews point to particular trends and practices on which the Program could focus in future years in order to enhance cost efficiency.

  - Building in-house science capacity: Recruiting new staff allows for knowledge transfer from senior-level scientists and helps the Program to achieve its goals and expected activities for the funded period. Interviews with senior management suggest that, given the critical nature and high relevance of this Program, there could be value added to having permanent staff to carry out the Program’s research activities.

  - Partnerships and links with the Canadian climate research community: One of the Program’s strengths relating to cost efficiencies are the synergies created with research networks in universities, regional research groups and regional Environment Canada staff, which enhance internal research capacity, reduce duplication of effort and save on some overhead costs. The CCCma, CCCSN and hazards component have taken advantage of collaboration opportunities for research by embedding Environment Canada scientists within Canadian universities in order to harness scientific expertise for achieving the goals of the Program. Interview respondents and internal documents also point to the creation of regional nodes as a means through which the CCCSN has created specific centres of expertise in order to better direct research efforts.

  - CCCSN Training workshops: The workshops, offered by the CCCSN, are designed to teach researchers and other target users how to access and utilize the data available on the CCCSN website. External interviewees and training workshop evaluations have pointed to the high utility of these sessions as well as their capacity to reach many members of the target population at once, saving time and effort among staff in explaining how to use the websites.

| Issue 5: Demonstration of Economy | Indicator(s) | Methods | Rating |
| --- | --- | --- | --- |
| Is the Program achieving its outcomes at the lowest cost possible? Are there alternative, less costly activities and deliverables that the Program could employ to achieve the same outcomes? | Cost analysis of resource utilization in relation to progress toward intended outcomes Presence/absence of less costly alternatives that would achieve the same results Opinions of key informants on whether or not the Program is achieving its outcomes at the lowest possible cost. | Document review Key informant interviews Review of financial information | Progress made, attention needed |

Although sufficiently detailed financial information was not available to assess the economy of the Program, less costly training activities were suggested that may achieve the same outcomes.

- A full cost analysis of resources expended against the achievement of outcomes could not be completed because there was a lack of detailed financial information that clearly links outputs and activities to their associated costs. Mid-year reviews outlined the achievements of the Program components but did not link these achievements with associated costs.

- Most key informants were not able to provide examples of less costly activities and outputs that would achieve the same outcomes. Some key informants, however, suggested some alternatives to CCCSN training that they felt would achieve the same outcomes. For example, an online training system for distance learning could be developed for data and website users or training could be integrated into university curricula in order to increase awareness, availability and access to research, websites and climate models.

# 5.0	CONCLUSIONS

The following conclusions on the Program’s relevance and performance have been developed based on evaluation findings and analyses:

- The Improved Climate Change Scenarios Program is relevant in meeting climate change information needs and is aligned with governmental priorities and federal roles and responsibilities.

The Program is fundamental in its provision of foundational data and information on climate change and its impacts.  Because the Program’s objectives and activities provide specialized scientific research on climate change and its impacts, its relevance is linked to the Government of Canada’s broader policy objectives and priorities related to climate change issues.  Program activities, outputs and intended outcomes are aligned with Environment Canada’s priorities to improve knowledge and information on weather and environmental conditions to influence decision-making. These data and information help to influence changes to infrastructure design that take into account present and future climate hazards and extremes, ultimately contributing to protect the safety and security of Canadians and their property.

There is a legitimate role and responsibility for the federal government to deliver this program because, without these data and information, Canada would be more vulnerable to climate change and its impacts that pose considerable threat to the health and well-being of Canadians.  This evaluation demonstrates that the federal government has a necessary role and responsibility in carrying out climate modelling, establishing and operating climate monitoring networks, conducting impacts and adaptation research in response to policy needs and providing national leadership in the direction, co-ordination, and funding of climate science in Canada.  The Government of Canada is well suited for this role because it is able to provide the large amount of scientific expertise, resources, infrastructure and capacity (including technical capacity) needed to address climate change impacts for the long-term.  Other programs and organizations involved in similar activities are complementary rather than duplicative the Program.  As well, there is a need for centralization to provide consistent information and quality data with an independent, national perspective that can contribute to the international scientific community.  Because climate change is a global phenomenon that must be addressed in concert with other countries, the Program’s research activities in the international scientific community contribute to shared knowledge and understanding of climate change and its impacts around the world.

- Current resource levels and difficulties in staffing pose a challenge for the Program in achieving its expected outcomes, particularly for the hazards and extremes component of the program.

There is a clear tension between expectations for the Program to achieve its intended outcomes and its ability to deliver on its commitments fully. The Improved Climate Change Scenarios Program is a science-based initiative that relies on the expertise of its scientists to meet its research objectives and achieve its expected outcomes. Adaptation funding for this program was intended to provide salary dollars for new work on climate modelling, climate change scenarios and, in particular, hazards and extremes research. Because there were delays in receiving Adaptation funding, the Program was unable to staff positions as planned to complete the work required. Departmental funding adjustments during the second year of implementation also had a negative impact on the Program’s ability to achieve its intended outcomes. For example, there were delays in completing research on settlements in the North and AIRS was not able to complete on time its extreme event analyses to support the development of new national codes and standards. The activities and intended outcomes are not considered to be realistic as originally planned given the Program’s capacity, particularly for the hazards and extremes component, which required the highest number of positions to be staffed.

- The Program could be improved by expanding its reach and providing more useful information to target audiences.

One of the Program’s strengths relating to cost-efficiencies are the synergies created with research networks in universities, regional research groups and regional Environment Canada staff in order to harness scientific expertise to achieve program objectives.  These networks and partnerships have reduced duplication of effort, saved on overhead costs and have led to greater collaboration to address climate change issues.  However, improvements could be made to the kinds of partnerships and networks possible. For example, increased partnerships with regional organizations could lead to more joint research projects and stronger connections with other federal departments could increase communication and coordination of climate change research activities across the federal government.  As well, CCCSN training workshops and information sessions for the hazards component of the Program were generally well-received by target audiences, but key informants felt that these reach only a portion of their potential target users. By expanding the reach of these sessions, awareness could be raised among more target users of the Program’s products (e.g., websites, research) and could facilitate their use and application of the Program’s climate change data and information. Expanding the Program’s partnerships and networks through improved outreach activities could enhance its ability to achieve its expected outcomes.

As well, the Program could be improved by providing more useful information. Climate change impacts are not experienced on a global scale; extreme weather events are experienced locally and adaptive strategies therefore need to be locally focused to be effective.  In particular, regionally or locally focussed information is more useful than national or global information for external partners.    The general consensus across internal and external partners, however, is that regionally focussed climate change information is generally not sufficiently available, particularly for the North given the greater rate of climate change in this area and the impact for northern communities. As well, technical committees for developing infrastructure among external partners require updated data and information on climatic design values to support the development of new national codes and standards. Without these updated data and information, Canadians are increasingly vulnerability to the negative impacts of climate change.

- The Program is generally being implemented as planned but the lack of ongoing performance data created difficulties in demonstrating the full performance story.

The evaluation found that the comprehensiveness and appropriateness of the Program’s performance data could be improved.  For example, a performance measurement plan for the Program was developed but this framework is not fully populated and the performance indicators that were identified lack sufficient specificity to provide useful measures of the Program’s progress towards achieving intended outcomes. Performance data were available but some of this information was highly scientific and technical such that its complexity limited its usefulness in the evaluation.  This evaluation demonstrates that, despite some delays, the Program is being implemented as planned but the lack of ongoing performance information for all program activities and outputs makes it difficult to assess the achievement of expected outcomes.

# 6.0	RECOMMENDATIONS

The following recommendations were developed based on evaluation findings and conclusions.  Given that the evaluation demonstrated the relevance of the Program and that program activities are on track for achieving expected outcomes, these recommendations are provided to improve on performance should decisions be made to continue the Program.  These recommendations are directed to the Assistant Deputy Minister (ADM) of the Science and Technology Branch.

Recommendation 1: Develop and implement a plan forward that considers the best utilization of the Program’s capacity when establishing priority commitments.

It is not clear that the Program will be able to deliver on all of its expected commitments, particularly for the hazards and extremes component. Available financial resources created challenges for the Program to staff as planned in order to carry out all of its planned research and research-related activities. Therefore, the Program should reconsider its expectations to deliver on all of its commitments. Prioritizing expected deliverables according to departmental needs and the needs of its stakeholders and partners might prove beneficial. Considering existing resource levels, the Program should then explore and implement ways to meet those priority commitments that would have the greatest negative impact if not delivered.

Recommendation 2: The Program should consider ways to increase their reach to target audiences and enhance their ability to meet target users’ climate change information needs, within the context of the Program’s capacity.

CCCma, CCCSN and the hazards and extremes component each have a specific target population for their climate change data and information, each with a specialized area of expertise and research interests. The general consensus among stakeholders is that the Program produces good research and its scientists are well-respected in Canada and internationally, but there was concern expressed that the Program’s climate change data and information were not reaching as large an audience as possible. The Program, therefore, should explore options to increase reach, such as expanding its partnerships and networks with regional organizations and other federal departments to facilitate increased use and application of its products for CCCma, CCCSN and the hazards and extremes component.

The Program’s target audiences have specific climate change information needs and are more likely to use data if they are useful for their needs. The general consensus among Program partners is that more climate change data and information specific to the regions are required, particularly for the North. As well, updated climatic design values are imperative for developing infrastructure that takes extreme climate conditions into account. The Program, therefore, should explore viable options of how to expand its research and related activities to include more climate change data and information that meet these needs. The Program may also consider consulting with stakeholders and partners to identify other key data and information required by target users in order to increase their usefulness further.

Recommendation 3: Develop a performance measurement framework that includes a clear strategy for ongoing data collection for reporting.

While program objectives were clearly identified in program documents, a clear strategy for measuring progress towards achieving these objectives was not as evident. A performance measurement plan was available but it was not fully populated and performance indicators were not sufficient to provide accurate, ongoing measures of the Program’s progress towards achieving outputs and intended outcomes. Therefore, the Program should ensure that a complete performance measurement strategy is developed and implemented that includes specific, measurable performance indicators with specific targets and timelines for measuring progress. When developing these indicators, the Program should explore ways to translate its complex, scientific data into useful information for reporting so that the full meaning of the output being measured is not lost. The Program should also develop a formal mechanism (e.g., a management information system) that organizes these performance measures together, including ongoing financial information, and data collection should be coordinated to ensure that ongoing performance measurement facilitates departmental reporting and future evaluation of the Program’s performance.

# 7.0	MANAGEMENT RESPONSE

The ADM of the Science and Technology Branch accepts the evaluation and all of its recommendations.  Provided the Improved Climate Change Scenarios Program and associated funding is renewed, the following management actions have been developed in response to these recommendations to improve on activities related to climate modeling, climate change scenarios and hazards and extremes research.

| Recommendation 1 |
| --- |
| Develop and implement a plan forward that considers the best utilization of the Program’s capacity when establishing priority commitments. |
| Statement of Agreement / Disagreement |
| Management agrees with the recommendation. |
| Management Action |
| The evaluation showed that the Program is, by and large, on track to being implemented as planned; however, in order to allow completion of work on hazards and extremes that was delayed at the outset, the Program plans to meet all of its remaining priorities by seeking program renewal beyond March 31, 2011 given that the evaluation has confirmed the relevance of the program. A plan for priority commitments will be established, wherein commitments will focus on the continuation of climate model development and further increases to the resolution of regional climate model projections to meet target audiences’ information needs. Priorities will be provision of climate data and information to specific regions, including the North, bridging and translation of new climate science on scenarios, hazards and extremes into relevant and accessible data products and tools for decision-makers, and continuation of partnerships to complete program deliverables on hazards for disaster management and infrastructure codes and standards. As part of this process, the Program will also consult with other sections within Environment Canada on cross-cutting activities that could be included in the plan forward under renewed funding. In addition, this consultation will address the broader issue of how best the federal government can facilitate the uptake and application of climate and adaptation science by target populations. Should the Program not be renewed beyond March 31, 2011 the Program will continue to focus on its current priorities, taking into account the Program’s current capacity, from now until March 31, 2011. |
| Timeline | Deliverable(s) | Responsible Party |
| March 31, 2011 | Assessment of Program’s current capacity and delivery of priority commitments. | Director General, ASTD |
| Within one year of commencement of new funding (pending future funding decisions) | A plan for addressing priority commitments under renewed funding. Evidence of consultations within Environment Canada (e.g., meeting minutes, memos, briefing notes). | Director General ASTD |

| Recommendation 2 |
| --- |
| The Program should consider ways to increase their reach to target audiences and enhance their ability to meet target users’ climate change information needs, within the context of the Program’s capacity. |
| Statement of Agreement / Disagreement |
| Management agrees with the recommendation as a suitable expectation for a renewed Adaptation program. |
| Management Action |
| The Program will continue to monitor stakeholder and partner information needs, and consider ways to increase its reach to target audiences and enhance its ability to meet target users’ climate information needs. These may include investing more heavily in delivery mechanisms, such as improved and more comprehensive provision of climate change information and supporting scientific data via web sites that have improved user interfaces, and by strategic implementation of user training workshops to reach target populations ready and capable of assimilating the information. It is important to note, however, that, to date, targeted stakeholder consultations with codes and standards agencies and provincial disaster management agencies have been completed. Training sessions on the use of climate change scenarios also continue to take place across Canada, including sessions provided upon request to stakeholders. In addition, over the coming months the new regional climate model will be in a position to provide more detailed region-specific information for all Canadians. Working within the broader EC community, will ensure that programs are developed to meet information and training needs of target populations, taking into consideration both resource and staffing issues. It would not be realistic to expand Program activities to increase its reach to target audiences and enhance its ability to meet target users’ climate change information needs without renewed funding. |
| Timeline | Deliverable(s) | Responsible Party |
| March 31, 2011 | Consultations with stakeholders and partners about information needs. | Director, CRD, ASTD Director General, ASTD |
| Within one year of commencement of new funding (pending future funding decisions) | Co-lead the development of an intra-interdepartmental strategic plan for improved client service through participation in meetings and decision-making processes. Improved delivery and accessibility of outputs to enhance user up-take of information in target populations. | Director, CRD, ASTD |

| Recommendation 3 |
| --- |
| Develop a performance measurement framework that includes a clear strategy for ongoing data collection for reporting. |
| Statement of Agreement / Disagreement |
| Management agrees with the recommendation as a suitable expectation for a renewed Adaptation program. |
| Management Action |
| On April 1st, 2010 the Department instituted a new Performance Measurement Framework (PMF) which includes detailed performance measurement reporting for both outcomes and outputs. The 2010/11 PMF outlines targets at the Output, Expected Result, and Strategic Outcome levels. At the Strategic Outcome, Expected Result and Output levels performance indicators have been identified for the hazards and extremes components of the Program e.g.: science input to new infrastructure / building codes, and climate projections and climate data sets on various time and spatial scales. These indicators are in line with the recommendations from the 2006 report by the Office of the Auditor General (CESD). At the Output level, a performance indicator for the climate modelling and projections component has also been identified. Accordingly, the data collection needed to report on these PMF indicators is now integrated within this overarching Departmental structure. Should the Program be renewed, it will seek additional opportunities and mechanisms to meet the near and longer term information needs of target populations, particularly in the context of climate service delivery, to which the Program would be an important contributor. The Program will carefully consider how to measure the performance of climate scientific research programs in a manner that takes into consideration the fact that the impacts of this research often take many years to manifest, and are dependent upon the capacity and abilities of target populations to assimilate. Therefore performance measurement strategies must focus on longer term performance measures dependent on capacity of target populations to change behaviour, and not solely individual programs. |
| Timeline | Deliverable(s) | Responsible Party |
| Completed | PMF for 2010/11. | WES Board Secretariat |
| March 31, 2011 | Fully populated PMF for 2010/11 for the Output, Expected Result, Evidence of continued data collection and reporting under the recently adopted PMF (e.g., web use statistics, surveys, stakeholder evaluations). | Director, CRD |
| Within one year of commencement of new funding (pending future funding decisions) | The Program will develop a performance measurement framework encompassing longer time frames, in the context of Canadian adaptive capacity. | Director General, ASTD |

# Annex 1 Adaptation Theme Logic Model

# Annex 2
Evaluation Issues and Questions

| Question | Indicators | Proposed Sources/Methods |
| --- | --- | --- |
| RELEVANCE |
| Issue 1: Continued Need for the Program |
| Are activities within the Program connected with key environmental climate change needs? | Degree to which the Improved Climate Change Scenarios Program continues to meet climate change adaptation needs | Document review Key informant interviews |
| Issue 2: Alignment with Government Priorities |
| 2. Are activities within the Program aligned with federal government priorities? | Degree of alignment between the objectives of the Improved Climate Change Scenarios Program and federal government priorities related to adaptation to climate change | Document review Key informant interviews |
| 3. Are activities within the Program aligned with the priorities of Environment Canada? | Extent to which the objectives of the Improved Climate Change Scenarios Program match mandate and priorities of Environment Canada Perceptions regarding the degree of alignment and examples of alignment between priorities of the Environment Canada and the Improved Climate Change Scenarios Program | Document review Key informant interviews |
| Issue 3: Alignment with Federal Roles and Responsibilities |
| Is there a legitimate and necessary role and responsibility for the federal government in the Improved Climate Change Scenarios Program? | Absence/presence of similar programs within the federal and/or provincial governments Extent to which similar programs complement or duplicate the Improved Climate Change Scenarios Program Perceptions and examples of gaps in meeting the climate change needs of Canadians without the Program | Document review Key informant interviews |
| PERFORMANCE (effectiveness, efficiency and economy) |
| Issue 4: Achievement of Expected Outcomes |
| 5. To what extent have intended outputs and early outcomes been achieved? |
| OUTPUTS |
| a) Tools, Processes and Systems | Evidence of enhanced global climate model and development of regional climate model Evidence of development of tools for climate change scenarios Evidence of updates to scenarios and hazards websites | Document review Key informant interview |
| b) Research | Number of peer-reviewed publications Program outputs in international assessments Evidence of the development of new research based on new climate models Evidence of methodologies examined for incorporating changing climate into infrastructure design | Document review Key informant interviews |
| c) Partnerships and Networks | Evidence of participation in research networks to develop new research Number of CCCSN servers deployed by region and by location Number of CCCSN training workshops conducted Number of regional sites added to hazards website Evidence of stakeholder organizations consulted | Document review Key informant interviews |
| IMMEDIATE OUTCOMES |
| d) Increased awareness of, availability of and access to research, websites and climate models | Number of data downloads and requests from all program websites Evidence of increased awareness of, availability of and access to global and regional climate models Evidence of increased awareness and improved knowledge on climate models among training sessions and workshop participants Evidence of improved access to hazards websites | Review of program documentation provided Key informant interviews File review |
| e) Greater collaboration within Canada and internationally to address climate change issues | Evidence of collaborations with key stakeholders and program partners, as demonstrated by: Co-authored publications Formal agreements Engagement with standards and codes agencies and industry associations | Document review Key informant interviews |
| INTERMEDIATE OUTCOMES |
| f) Increased use of websites and climate models among target populations | Perceptions among target populations on use of climate models and program websites in their own work | Document review Key informant interviews |
| g) Increased capacity to conduct climate change impacts and adaptation research among target populations | Demonstrated evidence of increased capacity to conduct climate change impacts and adaptation research as a result of the Program | Key informant interviews |
| h) Increased application of adaptation science and climate change research among target populations and appropriate jurisdictions | Demonstrated evidence that adaptation and climate change impacts research has been applied | Document review Key informant interviews |
| PROGRAM-LEVEL LONG-TERM OUTCOMES |
| j) User groups apply tools and information to assess climate change risks and plan adaptation strategies | Opinions that the research and related products from the Program were used to assess risks and inform the development of strategies and plans to prepare for future climate extremes Evidence of the adoption of new building codes that consider climate change risks | Document review Key informant interviews |
| i) Stakeholders have taken actions to reduce their vulnerabilities from and have adapted to predicted impacts of climate change | Perceptions that behaviours have changed as a result of the Program Examples of user groups that factor climate change risks into their planning/decision processes | Document review Key informant interviews |
| k) Risks to communities, infrastructure and to the health and safety of Canadians resulting from climate change have been reduced | Evidence of whether risks to the health of Canadians resulting from climate change have been reduced as a result of the Improved Climate Change Scenarios Program | Document review Key informant interviews |
| 6. Has the Program been implemented, or is it on track to being implemented, as planned? Are program activities, processes and governance structures adequate for achieving expected program results? | Extent to which performance data is comprehensive and appropriate Proportion of activities and outputs planned versus those completed Perceived adequacy of activities, processes and governance structures for achieving expected program results among program staff and partners Extent to which barriers to program implementation are identified and/or resolved | Document review Key informant interviews |
| Issue 5: Demonstration of Efficiency and Economy |
| Is the Program undertaking its activities and delivering its outputs at the lowest possible cost? How could the cost-efficiency of the Program’s activities be improved? Are there alternative, more cost-efficient means of achieving program outputs? | Cost analysis of resource utilization in relation to the production of outputs Opinions of stakeholders on the cost-efficiency of delivering program outputs and how it could be improved | Document review Key informant interviews Review of financial information |
| Is the Program achieving its outcomes at the lowest cost possible? Are there alternative, less costly activities and deliverables that the Program could employ to achieve the same outcomes? | Cost analysis of resource utilization in relation to progress toward intended outcomes Presence/absence of less costly activity and output alternatives that would achieve the same results Opinions of key informants on whether or not the Program is achieving its outcomes as cost-efficiently as possible | Document review Key informant interviews Review of financial information |

# Annex 3
List of Background Information and Supporting Documentation

Auld, H. (2009). Adaptation by design: The impact of a changing climate on infrastructure. The newsletter of the Adaptation and Impact Research Division, 11. Adaptation and Impact Research Division, Environment Canada.

Auld H. (2008). Disaster risk reduction under current and changing climate conditions. WMO Bulletin 57 (2).

Bizikova, L., Neale, T., and Burton, I. (2008). Canadian communities’ guidebook for adaptation to climate change. Including an approach to generate mitigation co-benefit in the context of sustainable development. First edition. Environment Canada and University of British Columbia, Vancouver.

Boettcher Crawford, Erica.  Bridging Science and Policy for Community Climate Change Adaptation: Is Climate Science “Usable” for Local Practitioners?, April 30 2009, p. 11.

Brooks, Mark, Gagnon-Lebrun, Frédéric, Harvey, Hélène and Sauvé, Claude (March 2009). Prioritizing Climate Change Risks and Actions on Adaptation: A Review of Selected Institutions, Tools and Approaches.  Policy Research Initiative, Ottawa, ON.

Cohen, S. (2009). British Columbia municipalities adapting to climate change. The newsletter of the Adaptation and Impact Research Division, 11. Adaptation and Impact Research Division, Environment Canada.

Commissioner of the Environment and Sustainable Development (CESD). (2006). Report of the Commissioner of the Environment and Sustainable Development to the House of Commons: Chapter 2: Adapting to the Impacts of Climate Change.

Dickinson, T.(2007). The Compendium of Adaptation Models for Climate Change: First Edition, Adaptation and Impact Research Division, Environment Canada, 42pgs. (ref provided)

Economics of Climate Adaptation (2009). Shaping Climate-Resilient Development: a Framework for Decision-Making.

Environment Canada and the Smithsonian Institution. (2008). Climate change and biodiversity in the Americas. Environment Canada and the Smithsonian Institution.

French, A., and MacLellan, J. (2009). Rapid assessment of the impacts of climate research (RAICC). The newsletter of the Adaptation and Impact Research Division, 11. Adaptation and Impact Research Division, Environment Canada.

Gleckler, P. J., Taylor, K. E., Doutriaux, C. (2008). Performance metrics for climate models, Journal of Geophysical Research, 113. P. 1-20.

Intergovernmental Panel on Climate Change (2007): Fourth Assessment of the Intergovernmental Panel on Climate	Change, Climate Change 2007: Synthesis Report.

Lemmen, D.S, Warren, F. J., Lacroix, J., and Bush, E., editors (2008); From Impacts to Adaptation: Canada in a Changing Climate 2007; Government of Canada, Ottawa, ON.

Mills, B. (2002). The road well travelled: Implications of climate change for pavement infrastructure in southern Canada. The newsletter of the Adaptation and Impact Research Division, 11. Adaptation and Impact Research Division, Environment Canada.

Mills, B., Unrau, D., Parkinson, C., Jones, B., Yessis, J., Spring, K. and Pentelow, L..(2009). Striking back: An assessment of lightning-related fatality and injury Risk in Canada. Adaptation and Impact Research Division, Environment Canada, Waterloo, Canada. 36p.

Mills, B., Unrau, D., Pentelow, L., and Spring, K. (2009).Flash Back: a review of lightning –related damage and disruption literature. Adaptation and Impact Research Division, occasional paper 16. Adaptation and Impact Research Division, Environment Canada.

Mirza, M. (2009). Vulnerability of and response to climate change in the cities of the Americas. The newsletter of the Adaptation and Impact Research Division, 11. Adaptation and Impact Research Division, Environment Canada.

National Round Table on the Environment and the Economy.  True North: Adapting Infrastructure to Climate Change in Northern Canada. 2009, p. 85-86.

Office of the Auditor General of Canada (2006).  The 2006 Report of the Commissioner of the Environment and Sustainable Development, Chapter 2: Adapting to the Impacts of Climate Change.

Toronto Region Conservation Authority (TRCA).  Meeting the Challenge of Climate Change: TRCA Action Plan for the Living City, p. 13.

Warren, F.J. and Egginton, P.A. (2008): Background Information; in From Impacts to Adaptation: Canada in a Changing Climate 2007, edited by D.S. Lemmen, F.J. Warren, J. Lacroix and E. Bush; Government of Canada, Ottawa, ON. P.29.

Williams, K. D., Webb, M. J. (2009). A quantitative performance assessment of cloud regimes in climate models.	Climate Dynamics, 33-1. p. 141–157. Retrieved February 26, 2010 from http://www.springerlink.com/content/t4612gv626q2hn44/

# Annex 4
Summary of Findings

| Evaluation Question | Achieved | Progress Made; Attention Needed | Little Progress; Priority for Attention | Too Early to Observe | Not Applicable |
| --- | --- | --- | --- | --- | --- |
| Relevance |
| Continued need for the Program | ( |  |  |  |  |
| Alignment with federal government priorities | ( |  |  |  |  |
| Alignment with departmental priorities | ( |  |  |  |  |
| Alignment with Federal Roles and Responsibilities | ( |  |  |  |  |
| Performance |
| 5a. Achievement of expected outputs | ( |  |  |  |  |
| 5b. Achievement of immediate outcomes | ( |  |  |  |  |
| 5c. Achievement of intermediate outcomes |  | ( |  |  |  |
| 5d. Achievement of long-term outcomes |  |  |  | ( |  |
| Implementation of program is on track for achieving expected results |  | ( |  |  |  |
| Demonstration of Efficiency |  | ( |  |  |  |
| Demonstration of Economy |  | ( |  |  |  |

# Footnotes

In addition to the Improved Climate Change Scenarios Program, the other programs under the Adaptation Theme include: Assist Northerners in Assessing Key Vulnerabilities and Opportunities – Climate Change (INAC), National Air Quality and Health Index (NAQHI) and Forecast Program (EC and HC), Climate Change and Health Adaptation in Northern and Inuit Communities (HC), Innovative Risk Management Tool (NRCan), Regional Adaptation Action Partnerships (NRCan) and Climate and Infectious Disease Alert and Response System to Protect the Health of Canadians (HC and PHAC).

These themes are led by Environment Canada (EC), Health Canada (HC), Transport Canada (TC) and Natural Resources Canada (NRCan), in partnership with Inuit and Northern Affairs Canada (INAC), Public Health Agency of Canada (PHAC), the National Research Council (NRC) and the Department of Foreign Affairs and International Trade (DFAIT).

Lemmen, D.S, Warren, F. and J., Lacroix (2008); Synthesis in From Impacts to Adaptation: Canada in a Changing Climate 2007, edited by D.S. Lemmen, F.J. Warren, J. Lacroix and E. Bush; Government of Canada, Ottawa, ON. P.4.

In addition to the Improved Climate Change Scenarios Program, the other programs under the Adaptation Theme include: Assist Northerners in Assessing Key Vulnerabilities and Opportunities – Climate Change (INAC), National Air Quality and Health Index (NAQHI) and Forecast Program (EC and HC), Climate Change and Health Adaptation in Northern and Inuit Communities (HC), Innovative Risk Management Tool (NRCan), Regional Adaptation Action Partnerships (NRCan) and Climate and Infectious Disease Alert and Response System to Protect the Health of Canadians (HC and PHAC).

Lemmen, D.S., Warren, F.J. and J. Lacroix (2008): Synthesis: in From Impacts to Adaptation: Canada in a Changing Climate 2007, edited by D.S. Lemmen, F.J. Warren, J. Lacroix and E. Bush; Government of Canada, Ottawa, ON p.1-20.

Although climate change scenarios use global climate models in its projections, AIRS uses multiple global climate models from other countries, not only the Canadian global climate model, to improve the robustness of its estimates.

Global climate models can focus on oceanic or atmospheric circulation, for example, or they can be “coupled” to link these separate processes together for a more comprehensive representation of climate change projections.  These coupled models, however, are extremely complex and difficult to interpret, and are still being developed.

The CCCma has already developed the first Canadian global climate model, called the Canadian Earth System Model (CanESM1).  Program funding was intended to facilitate the development and testing of the second Canadian global model, Can ESM2.

Other countries, such as Japan, Germany, and the United States, have also developed their own global models based on their own climate data.

An existing regional climate model is run by the Ouranos consortium in Quebec in collaboration with the CCCma.

The nodes of the CCCSN include the Ontario node at the University of Toronto, the Quebec node at McGill University (also connected to Ouranos), the Prairie node at the University of Regina, the Arctic node at Yukon College in Whitehorse, the Pacific-Yukon node at the University of British Columbia and the Atlantic node at the University of Prince Edward Island.  The Ontario node is the primary site for network development and administration and houses the main server for the CCCSN website.

Commissioner of the Environment and Sustainable Development. (2006)  Report of the Commissioner of the Environment and Sustainable Development to the House of Commons. Chapter 2: Adapting to the Impacts of Climate Change.

The Improved Climate Change Scenarios program is implemented across the country within various Environment Canada regional offices as well as within several research facilities.  While the director of the CRD operates out of Environment Canada’s regional office at the Downsview facility in Toronto, program officers in CCCma and AIRS are located across Canada.  The majority of CCCma officers are situated at the University of Victoria; however, a few CCCma staff members are located in Montreal (at the Ouranos research centre and the Environment Canada Dorval office) and in Toronto’s Downsview facility.  The majority of AIRS officers are situated in the Downsview facility with a few positions in Montreal (at the Dorval office, McGill University and l’Université de Québec à Montréal), at the University of Toronto and at York University.

These senior management committees include: the Deputy Minister Committee, the Assistant Deputy Minister (ADM) Steering Committee, the Director General Theme Leads Coordinating Committee (DGTLCC) and the Director General Management Committees (DGMC) for each Theme.

The first chair of the Adaptation Theme DGMC was the DG of ASTD at Environment Canada.  In 2009-10, the DG of Climate Change Impacts and Adaptation Directorate at NRCan became chair.

The 30% estimate for 2008-09 does not include AIRS because AIRS was not part of CRD at this time.  Information for AIRS alone was not available.

In response, the Atmospheric Science and Technology Directorate (ASTD) transferred funds from other activities within the directorate as an interim solution to offset these budget shortfalls.  ASTD also transferred O&M funding from among other ASTD programs to provide sufficient A-Base O&M for climate modelling activities.

Economics of Climate Adaptation (2009). Shaping Climate-Resilient Development: a Framework for Decision-Making, p.10

Intergovernmental Panel on Climate Change (2007): Fourth Assessment of the Intergovernmental Panel on Climate Change, Climate Change 2007: Synthesis Report.

Brooks, Mark, Gagnon-Lebrun, Frédéric, Harvey, Hélène and Sauvé, Claude (March 2009). Prioritizing Climate Change Risks and Actions on Adaptation: A Review of Selected Institutions, Tools and Approaches.  Policy Research Initiative, Ottawa, ON.

Lemmen, D.S., Warren, F.J., Lacroix, J., and Bush, E., editors (2008): From Impacts to Adaptation: Canada in a Changing Climate 2007; Government of Canada, Ottawa, ON, p.3.

Office of the Auditor General of Canada (2006).  The 2006 Report of the Commissioner of the Environment and Sustainable Development, Chapter 2: Adapting to the Impacts of Climate Change.

Brooks, Mark, Gagnon-Lebrun, Frédéric, Harvey, Hélène and Sauvé, Claude (March 2009). Prioritizing Climate Change Risks and Actions on Adaptation: A Review of Selected Institutions, Tools and Approaches.  Policy Research Initiative, Ottawa, ON.

Office of the Auditor General of Canada (2006).  The 2006 Report of the Commissioner of the Environment and Sustainable Development, Chapter 2: Adapting to the Impacts of Climate Change.

Environment Canada’s 2B5 Adaptation and Impacts Science Plan: An Adaptation and Impacts Science Strategy 2009-2012, the division/section’s four-year work plan that addresses the impacts and adaptation science component of the broader departmental plan, Environment Canada’s Science Plan: A Strategy for Environment Canada’s Science.  A similar science plan was not evident for climate modelling activities.

Commissioner of the Environment and Sustainable Development (CESD).  Report of the Commissioner of the Environment and Sustainable Development to the House of Commons: Chapter 2: Adapting to the Impacts of Climate Change2006, p. 7.

Climatic design values refer to measures of climate conditions that have been analyzed and provided for national codes and standards that govern the design requirements for infrastructure.  Climatic design values include quantities like the rainfall or weight of snowpack conditions or percentile cold, hot or humid temperature or humidity conditions that are typically derived from historical climate data.

National Round Table on the Environment and the Economy.  True North: Adapting Infrastructure to Climate Change in Northern Canada. 2009, p. 85-86.

This model is being developed in collaboration with the Department of Fisheries and Oceans.

Research was considered to be within the scope of this evaluation if the publication date was between 2007 and 2009.  Given the delays in the publication process, however, these publications were likely based on research conducted prior to 2007.

Gleckler, P. J., Taylor, K. E., Doutriaux, C. (2008). Performance metrics for climate models, Journal of Geophysical Research, 113. P. 1-20.

Williams, K. D., Webb, M. J. (2009). A quantitative performance assessment of cloud regimes in climate models. Climate  Dynamics, 33-1. p. 141–157. Retrieved February 26, 2010 from http://www.springerlink.com/content/t4612gv626q2hn44/

This is defined as those having a couple of courses related to meteorology.  Even among this 1200, many are likely not to have sufficient expertise and experience to meet the requirements of the job for hazards and extremes research.

This international search poses its own challenges since the position must be sufficiently appealing to draw qualified candidates to Canada and staffing actions must follow HR policy.

It is not clear from the evidence why this decline occurred but the number of data downloads from the CCCma website are likely conservative estimates as they do not take into account the CCCma climate model data that are available for downloading from other international websites, which were out of scope for this evaluation.

Participants are typically scientists who use adaptation science in their own work including, for example, academics, university students, officers from research organizations and other federal departments, municipal planners and conservation authorities, provincial partners and community officers.

Workshops were held in Toronto, Regina, Fredericton and Whitehorse with an average of 22 participants per workshop.

Questions are answered individually by one program officer in the midst of other responsibilities.

Boettcher Crawford, Erica (2009).  Bridging Science and Policy for Community Climate Change Adaptation: Is Climate Science “Usable” for Local Practitioners?

Types of climate information included: Risk or vulnerability assessment information, weather or seasonal climate forecasts, projections of specific climatic changes, regional or local climate projections, national or global climate projections, case studies from other jurisdictions, costing of adaptation options, information on best practices and guidebooks on adaptation to climate change.  (n=31 communities)

Boettcher Crawford, Erica.  Bridging Science and Policy for Community Climate Change Adaptation: Is Climate Science “Usable” for Local Practitioners?, April 30 2009, p. 11.

Toronto Region Conservation Authority (TRCA).  Meeting the Challenge of Climate Change: TRCA Action Plan for the Living City, p. 13.

Performance indicators like “publication of new scientific results,” “research and analysis to enhance methodologies” or “research and analysis to develop scenarios tools for climate extremes,” for example, are not appropriately defined or bounded to provide useful measures of achievement of outputs and intended outcomes.

The Program was already experiencing financial pressures from the decision to redirect Climate Change Interim Strategy (CCIS) funds away from ASTD activities in 2007-08 and reallocate ASTD funding to other parts of the department in 2008-09 to offset the impact of the sunsetting of CCIS.  Adaptation funding was intended to be incremental but CCCma and AIRS activities relied almost completely on this funding during this time.

More than half of this funding was intended to be used to hire new scientists.

According to the Clean Air Agenda Horizontal Performance Report 2008-2009, planned spending was $5,210,730 while the actual amount spent totalled $3,567,788.  (Figures for other years were not available at time of reporting.)  This report also notes that $1,220,000 of this unused funding was to be carried forward to the following two years of the program.